## README
Annual Progress Report for AB 617 Community Emissions Reduction Programs
DRAFT Data Collection Template - San Bernardino/Muscoy
Purpose: Use this Excel spreadsheet template to provide status updates for each strategy, as identified in your community emissions reduction program. Attach this spreadsheet to the Microsoft Word template that describes overall progress for your program. This spreadsheet includes the following tabs:
CARB Metrics: This workbook summarizes the metrics CARB will use to track progress of statewide strategies in the "Community Emissions Reduction Plan, San Bernardino, Muscoy" (San Bernardino, Muscoy Plan). The CARB strategies included in the San Bernardino, Muscoy Plan are grouped into three categories with a separate tab for each: Regulatory, Enforcement, and Guidance. The CARB Incentives tab provides metrics for incentive projects that are located in the San Bernardino, Muscoy community and are funded by a statewide incentive program.
1. CARB Regulatory Metrics: | CARB regulatory metrics track CARB's regulatory development process for strategies identified in the San Bernardino, Muscoy Plan. These metrics are cumulative since the initiation of regulatory development.
2. CARB Enforcement Metrics: | CARB enforcement metrics are cumulative since 2019.
3. CARB Guidance Metrics: | CARB guidance metrics track CARB's guidance development process and are cumulative since the initiation of guidance development.
4. CARB Incentive Metrics: | CARB incentive metrics are cumulative since 2017.
DISTRICT Metrics: This workbook also summarizes the metrics that the South Coast Air Quality Management District (SCAQMD) will use to track progress of district strategies included in the "Community Emissions Reduction Plan, San Bernardino, Muscoy" (San Bernardino, Muscoy Plan).
5b to 5g. DISTRICT Metrics: | DISTRICT metrics track the progress of all strategies that are not included on the CARB tabs, as listed in Chapters 5b to 5g of the San Bernardino, Muscoy Plan.
REFERENCES
CARB Community Air Protection Blueprint, October 2018, Appendix C, pages C-38 to C-40
https://ww2.arb.ca.gov/our-work/programs/community-air-protection-program/community-air-protection-blueprint
Community Emissions Reduction Plan, San Bernardino, Muscoy, September 6, 2019
https://www.aqmd.gov/nav/about/initiatives/community-efforts/environmental-justice/ab617-134/san-b/cerp-docs
CARB document CARB document “San Bernardino, Muscoy, Community Emissions Reduction Program Staff Report” released March 26, 2020, available at:
https://ww2.arb.ca.gov/resources/documents/san-bernardino-muscoy-community-emissions-reduction-program-staff-report
SCAQMD Board Resolution 19-28, approved at a Board Meeting on September 6, 2019, available at
https://www.aqmd.gov/nav/about/initiatives/community-efforts/environmental-justice/ab617-134/san-b/cerp-docs
CARB Board Resolution -TBD
QUESTIONS? Send an email to: | CommunityAir@arb.ca.gov
Date last modified: | Version | CARB Authors
2020-07-10 | 1.0 | Jeremy Herbert; Tom Olson; Hanjiro Ambrose; Monique Davis
Policy metrics vintage - April 30, 2020
Incentive metrics vintage - TBD
Enforcement metrics vintage - TBD
Guidance metrics vintage - April 30, 2020
CARB-Air District Discussion Only ¦ Draft Deliberative

## 1.CARB Regulatory
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
|  |  |  | Outreach |  |  | Non-Regulatory Documents |  |  |  | Regulatory Process Milestones | [5 empty] | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable) |  | Community Criteria and Toxics Emissions Forecasted Baseline Emissions (tpy) (2024) | [8 empty] | Community Criteria and Toxics Emissions Draft Emissions Reductions, As Available (tpy) (2024) | [8 empty] | Community Criteria and Toxics Emissions Final Emissions Reductions (tpy) (2024)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | CARB Regulation | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Non-Regulatory Document(s) (Text) | Draft Document Release(s) (Date) | Final Document Release(s) (Date) | Workshops/Webinars | Release of 45 day or 60 day package | First Board hearing | Potential 15 day changes | Final Board hearing | OAL approval | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM
Action 1 | 5e-4 | Reduce emissions from railyards by development of indirect source rule; working with CARB to develop new requirements; working with local utilities and state agencies to encourage ZE infrastructure installation; continuing to support CARB's USEPA petition for new national locomotive emission standards; working with railyards to replace diesel fueled equipment with cleaner technologies; and using emissions inventory and air monitoring information to identify possible emissions reductions. | Evaluation and Potential Development of Regulation to Reduce Emissions from Locomotives and Railyards | 2 | 95 | Los Angeles, San Bernardino | 1 | 1. Presentation: Concepts to Reduce Emissions from Locomotives and Railyards | * | 1. 11/19/2019 | 2 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. Public outreach (South Coast November/December 2019); Air District and Railroad meetings; Internal Development work – Start of draft inventory update, Health Risk Characterization and monetization. b. The health related emissions reductions and exposure reduction benefits will be described in next round of outreach later in 2020. c. N/A | a. N/A b. N/A c. N/A | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Action 1 | 5e-4 | Reduce emissions from railyards by development of indirect source rule; working with CARB to develop new requirements; working with local utilities and state agencies to encourage ZE infrastructure installation; continuing to support CARB's USEPA petition for new national locomotive emission standards; working with railyards to replace diesel fueled equipment with cleaner technologies; and using emissions inventory and air monitoring information to identify possible emissions reductions. | Cargo Handling Equipment Regulation to Transition to Zero-Emissions | 0 | 0 | * | 1 | 1. Cargo Handling Equipment Regulation to Transition to Zero-Emissions | * | 1. 3/14/2018 | 0 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. Tracking existing demonstration and pilot projects, meeting with some terminal operators to better understand operations and perspectives on zero-emission operation, participating in port air quality plan workgroups, task force meetings, and other updates b. Targeting transition to zero-emission tailpipe technologies where possible. Exact targets expected in 2022. c. Zero-emission equipment will likely require additional infrastructure to be installed at facilities for operation of equipment, charging of on-board batteries, and fueling with alternative (i.e. zero-emission tailpipe) fuel. Substantial terminal reconfiguration and/or construction may be required. | a. N/A b. N/A c. N/A | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Action 1 | 5e-4 | Reduce emissions from railyards by development of indirect source rule; working with CARB to develop new requirements; working with local utilities and state agencies to encourage ZE infrastructure installation; continuing to support CARB's USEPA petition for new national locomotive emission standards; working with railyards to replace diesel fueled equipment with cleaner technologies; and using emissions inventory and air monitoring information to identify possible emissions reductions. | Transport Refrigeration Unit Regulation | 8 | 641 | Fontana, Fresno, Riverside, Sacramento, Teleconference | 1 | 1. Transport Refrigeration Unit Regulation Draft Regulatory Language for Stakeholder Review | * | 1. 3/12/2020 | 8 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. CARB has been developing the TRU Regulation since 2016, expects adoption in 2021, and will begin implementation in 2022. b. TRU regulation will provide health, air quality, and climate benefits by reducing NOx, PM2.5, and GHG emissions. c. Installation of electric or fueling infrastructure at approximately 900 truck TRU home base facilities and 6,100 applicable facilities statewide. | a. CARB expanded the scope of the TRU Regulation to include additional requirements for the use of lower global warming potential refrigerants and diesel emission standards for units that are not required to be fully zero emission. Additional time was also given to stakeholders to comment on draft regulation language, as provided by Governor Newsom’s Executive Order N-20-40 which authorizes additional time before formal rulemakings must be completed. b. Staff anticipate bringing the rulemaking to the Board in 2020 and 2021 (two hearings). c. The expanded scope of the TRU Regulation will achieve additional emissions and health risk reductions in the same timeframe of the original concept. Implementation will begin in 2021. | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Ongoing Efforts | 5b-3 | Drayage Truck Rule – Updated regulation to transition to zero-emission trucks. | Advanced Clean Fleet | 1 | 0 | Diamond Bar | 0 | * | * | * | 1 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. Staff have been developing the regulation since 2019, have held a public workshop to kick off the effort, and have begun having individual meetings with stakeholders. b. TBD c. TBD | a. N/A b. N/A c. N/A | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Ongoing Efforts | 5b-3 | Heavy-Duty Low NOx Rule – Would set new statewide engine standards for trucks. 60-75% NOx reduction between 2024-2026. Additional reductions in 2027 and beyond. | Heavy-Duty "Omnibus" Low NOx Rulemaking | 14 | 1060 | Diamond Bar, Sacramento, Webcast | 1 | 1. CARB Staff White Paper: California Air Resources Board Staff Current Assessment of the Technical Feasibility of Lower NOx Standards and Associated Test Procedures for 2022 and Subsequent Model Year Medium-Duty and Heavy-Duty Diesel Engines | * | 1. 4/18/2019 | 14 | 2020-06-30 | * | * | * | * |  | Proposed Heavy-Duty Engine and Vehicle Omnibus Regulation and Associated Amendments will be tentatively first heard on 8/27/20 | a. Research contracts, workgroup and workshops, met engine manufacturers, component manufacturers, US EPA, outreach. b. NOx is a precursor to ozone and secondary PM formation. Californians would benefit from reduced emergency room and doctor’s office visits for asthma, reduced hospitalizations for worsened heart diseases, and reduced premature death. This in turn would result in reduced asthma-related school absences, reduced sick days off from work, reduced health care costs, and increased economic productivity. c. None | a. N/A b. N/A c. N/A | 176.468 | * | * | * | * | * | * | * | * | 0.51222 | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Ongoing Efforts | 5b-3 | Advanced Clean Truck Rule – Mandate for truck manufacturers to sell zero-emission trucks and would require fleet reporting. By 2030, there will be a zero-emission truck/chassis sales requirement. | Advanced Clean Trucks | 13 | 441 | Sacramento | 4 | 1. Factsheet 2. ACT Truck Market Segment Analysis 3. Total Cost of Ownership Discussion Document 4. Battery-Electric Truck and Bus Energy Efficiency Compared to Conventional Diesel Vehicles | * | 1. 7/2/2019 2. 2/25/2019 3. 2/25/2019 4. 5/1/2018 | 13 | 2019-10-22 | 2019-12-12 | 2020-04-28 | 2020-06-25 | * |  | The Advanced Clean Trucks first heard on 12/12/19. The 15-Day changes was posted 4/28/20. Comments close 5/28/20. The Advanced Clean Trucks was adopted on 6/25/20. | a. CARB has been developing the Advanced Clean Trucks regulation since 2016, expects adoption in 2020 and will begin implementation in 2024. b. As a result of the Advanced Clean Trucks regulation, from 2020 to 2040, NOx and PM2.5 emissions are estimated to be cumulatively reduced by 58,313 tons and 1916 tons, respectively. From 2020 to 2040, the Proposed Modifications are expected to reduce GHG emissions by a cumulative 17.3 MMT CO2e. The estimated total statewide health benefits derived from criteria emission reductions are estimated to be $8.9 billion from 2020 to 2040. From 2020 to 2040, statewide avoided premature deaths are estimated to be 943, avoided hospitalizations for cardiovascular illness are estimated to be 148, avoided hospitalizations for respiratory illnesses are estimated to be 177, and avoided ER visits are estimated to be 453. c. None, this is a manufacturer sales requirement. CEQA impacts include increased construction of EVSE infrastructure. | a. N/A b. N/A c. N/A | 193.202 | * | * | 6.0095 | * | * | * | * | 1.039 | 0.2157 | * | * | 0.0080416 | * | * | * | * | 0.0008403 | * | * | * | * | * | * | * | * | *
Ongoing Efforts | 5b-3 | Zero-Emission Fleet Rule – Would require fleets to transition to zero-emissions. | Advanced Clean Fleet | 1 | 0 | Diamond Bar | 0 | * | * | * | 1 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. Staff have been developing the regulation since 2019, have held a public workshop to kick off the effort, and have begun having individual meetings with stakeholders. b. TBD c. TBD | a. N/A b. N/A c. N/A | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Action 2 | 5b-6 | Work with local agencies (city and county) to designate truck routes and designated truck parking areas away from sensitive receptors; provide outreach to truck owners about community ordinances, restricted truck routes and regulations, identify incentives; support acceleration of zero-emission technology; targeting incentives to local small business; continue development of a facilities based mobile source measure (indirect source rule); train on complaint reporting; participate in future rule development by CARB for trucks; and conduct focused enforcement. | Heavy-Duty "Omnibus" Low NOx Rulemaking | 14 | 1060 | Diamond Bar, Sacramento, Webcast | 1 | 1. CARB Staff White Paper: California Air Resources Board Staff Current Assessment of the Technical Feasibility of Lower NOx Standards and Associated Test Procedures for 2022 and Subsequent Model Year Medium-Duty and Heavy-Duty Diesel Engines | * | 1. 4/18/2019 | 14 | 2020-06-30 | * | * | * | * |  | Proposed Heavy-Duty Engine and Vehicle Omnibus Regulation and Associated Amendments will be tentatively first heard on 8/27/20 | a. Research contracts, workgroup and workshops, met engine manufacturers, component manufacturers, US EPA, outreach. b. NOx is a precursor to ozone and secondary PM formation. Californians would benefit from reduced emergency room and doctor’s office visits for asthma, reduced hospitalizations for worsened heart diseases, and reduced premature death. This in turn would result in reduced asthma-related school absences, reduced sick days off from work, reduced health care costs, and increased economic productivity. c. None | a. N/A b. N/A c. N/A | 176.468 | * | * | * | * | * | * | * | * | 0.51222 | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
Action 2 | 5b-6 | Work with local agencies (city and county) to designate truck routes and designated truck parking areas away from sensitive receptors; provide outreach to truck owners about community ordinances, restricted truck routes and regulations, identify incentives; support acceleration of zero-emission technology; targeting incentives to local small business; continue development of a facilities based mobile source measure (indirect source rule); train on complaint reporting; participate in future rule development by CARB for trucks; and conduct focused enforcement. | Advanced Clean Fleet | 1 | 0 | Diamond Bar | 0 | * | * | * | 1 | * | * | * | * | * |  | This strategy requires CARB action during at least one board hearing. | a. Staff have been developing the regulation since 2019, have held a public workshop to kick off the effort, and have begun having individual meetings with stakeholders. b. TBD c. TBD | a. N/A b. N/A c. N/A | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | * | *
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 2.CARB Enforcement
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
|  |  |  | Outreach |  |  | Inspections |  |  |  | Coordination |  |  |  |  | SB 1 Implementation |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | Agency | Events within Community (Qty) | Attendees (Qty) | Locations of Events (Text) | Complaint Inspections (Qty) | CERP Inspections (Qty) | NOVs (Qty) | Compliance Rate (%) | Agencies Engaged (Qty) | Names of Agencies Engaged (Text) | Meetings (Qty) | Resulting Actions (Qty) | Description of Resulting Actions (Text) | Statewide Vehicle Turnover (Qty) | Community Registration Holds (Qty) | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Action 1 | 5b-4 | Reduce truck idling through focused enforcement; collaboration with CSC to inform community on idling reporting; engagement through outreach on existing idling complaint systems; and work with CARB and local agencies to put up no idling signs. | SCAQMD, CARB, CSC | None outside SCAQMD CSC meetings | SCAQMD has number of attendees |  | 0 | 95 | 2 | 98% | N/A |  | N/A | N/A |  | N/A | N/A |  | X |  |  |  | CARB ED strategies found in the Enforcement Plans in each CERP should not require action by either the CARB Board the Air District board. | CARB ED does not characterize the health-related emissions or exposure reduction benefits. CARB ED will begin to track the steps-taken to date moving into next years update. | Implementation for most CERPS began January 1, 2020. There currently, are no strategies behind the proposed due date in the Enforcement plan.
Action 2 | 5b-6 | Work with local agencies (city and county) to designate truck routes and designated truck parking areas away from sensitive receptors; provide outreach to truck owners about community ordinances, restricted truck routes and regulations, identify incentives; support acceleration of zero-emission technology; targeting incentives to local small business; continue development of a facilities based mobile source measure (indirect source rule); train on complaint reporting; participate in future rule development by CARB for trucks; and conduct focused enforcement. | SCAQMD, CARB, City or County of San Bernardino, CSC | N/A | N/A |  | 4 rec'd (2 tampering, 2 smoking vehicle); status unknown at time of publishing | 203 Truck & Bus; 378 Drayage | 1 Truck & Bus; 8 Drayage | 99.5% Truck & Bus; 98% Drayage | N/A |  | N/A | N/A |  | N/A | N/A |  | X |  |  |  | CARB ED strategies found in the Enforcement Plans in each CERP should not require action by either the CARB Board the Air District board. | CARB ED does not characterize the health-related emissions or exposure reduction benefits. CARB ED will begin to track the steps-taken to date moving into next years update. | Implementation for most CERPS began January 1, 2020. There currently, are no strategies behind the proposed due date in the Enforcement plan.
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 3.CARB Guidance
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | Outreach |  |  | Pre-Guidance Documents |  |  |  | Guidance Development Dates |  |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Page # in Blueprint | Strategy Description in CERP | Agency | CARB Guidance Title | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Document (Text) | Draft Document Released (Date) | Final Document Released (Date) | Draft Guidance Released | Final Guidance Released | Board Hearings | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Freight Facilities Handbook | 5c-3 |  | CARB’s actions to minimize community health impacts from freight. | CARB | Freight Handbook | 0 | 0 | * | 1 | 1. Concept Paper for the Freight Handbook | * | 1. 12/12/2019 | * | * | * |  | X |  |  | Currently, staff resources assigned to the development of a standalone Freight Handbook have been reprioritized to work on development of freight regulations. To ensure that the recommendations included in the Concept Paper for the Freight Handbook and public stakeholder input are utilized, CARB staff are working to integrate this information into the Community Air Protection Program Resource Center (https://ww2.arb.ca.gov/ocap_resource_center) | * | * | *
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 4.CARB Incentive
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB is providing the following information on incentive programs benefiting San Bernardino/Muscoy
South Coast AQMD: San Bernardino/Muscoy
|  | Outreach |  |  | Incentive Funding |  | Reductions
CARB Incentive Program | Agency | Events within Air District (Qty) | Attendees (Qty) | Locations of Events (Text) | Funding Amount ($) | Number of Projects (Qty) | PM 2.5 (tons) | ROG (tons)
Supplemental Environmental Project | CARB | 0 | 0 | * | 0 | 0 | * | *
California Climate Investments | CARB, State Agencies ** | 64 | 11819 | Anaheim, Burbank, Coachella, Commerce, Compton, Downey, East Los Angeles, Fullerton, Hawthorne, Irvine, Long Beach, Los Alamitos, Los Angeles, Muscoy, Palm Desert, Pomona, Riverside, San Fernando, San Gabriel, Santa Ana, Santa Clarita, Torrance, Whittier, Wilmington | 23073287 | 1217 | * | *
Low Carbon Transportation Investments and Air Quality Improvement Program | CARB, Air Districts | 5 | 300 | Los Angeles, Riverside, Temecula | 2424466 | 100 | * | *
Carl Moyer Memorial Air Quality Standards Attainment Program | CARB, Air Districts | 2 | 30 | Diamond Bar | 80000 | 2 | 0.02 | 0.62
Proposition 1B: Goods Movement Emission Reduction Program | CARB, Air Districts | 0 | 0 | * | 0 | 0 | * | *
School Bus Retrofit Program | CARB, Air Districts | 0 | 0 | * | 0 | 0 | * | *
FARMER | CARB, Air Districts | 2 | 1234 | * | 0 | 0 | * | *
Volkswagen Environmental Mitigation Trust for California | CARB | 0 | 0 | * | * | * | * | *
Community Air Protection Incentives | CARB, Air Districts | 16 | 1165 | Carson, Commerce, Heber, Los Angeles, San Bernardino | 9064442.07 | 33 | 5.699 | 3.3164
- This metric will not be tracked by CARB.
| * | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.
| ** | - For a list of all State Agencies that administer California Climate Investments, please refer to the current CCI annual report. http://www.caclimateinvestments.ca.gov/annual-report/

## CARB Metrics Glossary
Glossary of CARB Metrics
Description of metrics that CARB will track and provide to the District, as shown on the tabs in this spreadsheet.
METRICS | DESCRIPTIONS
Outreach
Events statewide (Qty) | Number of CARB outreach/training events.
Attendees (Qty) | Number of attendees at CARB outreach/training events.
Locations of Events (Text) | List locations where outreach events are held (e.g., city names)
Enforcement and Inspections
Complaint Inspections (Qty) | Number of complaint inspections conducted by CARB.
CERP Inspections (Qty) | Number of inspections based on CERP strategies and conducted by CARB.
NOVs (Qty) | Number of notices of violation (NOVs) issued in the community by CARB.
Compliance Rate (%) | Percentage of CARB inspections that were found to be in compliance with CARB regulations.
Statewide vehicle turnover | Number of heavy duty vehicles that have permanently stopped operating in California, as a result of SB 1 implementation.
Community registration holds | Number of heavy duty vehicle registrations in the community that have been denied due to non-compliance with SB 1 provisions.
Coordination
Agencies Engaged (Qty) | Number of agencies engaged by CARB.
Names of Agencies Engaged (Text) | List names of agencies engaged by CARB.
Meetings (Qty) | Number of CARB meetings with other agencies
Resulting Actions (Qty) | Number of actions resulting from coordination with other agencies.
Description of Resulting Actions (Text) | Provide a brief description of actions resulting from coordination with other agencies.
Non-Regulatory Documents (concept papers, white-papers, etc.)
Public Documents Released (Qty) | Number of public document(s) released
Title of Non-Regulatory Document(s) (Text) | Title of non-regulatory document(s) associated with the development of statewide measures
Draft document released (Date) | Date when CARB released the draft non-regulatory document(s)
Final document released (Date) | Date when CARB released the final non-regulatory document(s)
Regulatory Process Milestones
Workshops/Webinars | Number of public workshop(s) or webinar(s) conducted providing the opportunity for stakeholders, including community members, to influence staff work prior to going to Board.
Release of 45 day or 60 day package | Start of Office of Administrative Law clock, providing the opportunity for stakeholders, including community members, to begin influencing Board member perspectives/decisions.
First Board hearing | Date when CARB's Governing Board holds initial public hearings (may be more than 1)
Potential 15 day changes | Date when CARB released "15-day changes" with revisions to draft regulatory language for public comment
Final Board hearing | Date when CARB's Governing Board approves the adoption of the regulation
OAL approval | Date when the California Office of Administrative Law approves the regulation
Community Criteria and Toxics Emissions Reductions Based on CARB’s Community-Scale Inventory
Forecasted baseline emissions (tpy) (2024) for all pollutants in planning inventory | Forecasted baseline emissions without the CARB measure
Draft emissions reductions, as available (tpy) (2024) for all regulatory pollutants in the planning inventory | Draft forecasted emissions reductions in 2024 with implementation of CARB measure, released during the regulatory development process
Final emissions reductions (tpy) (2024) for all regulatory pollutants in the planning inventory | Final forecasted emissions reductions in 2024 with implementation of CARB measure, after the regulation is adopted by CARB's Board

## 5b.DISTRICT Neighborhood Truck
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in Plan | Page # in Plan | DISTRICT STRATEGIES Chapter 5b-Neighborhood Truck Traffic | DISTRICT GOALS Goals for Each Strategy in Chapter 5b of San Bernardino/Muscoy Plan | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Neighborhood Truck Traffic-Action 1 | 5b-4 | Reduce Emissions from Illegal Heavy-Duty Truck Idling in the Community: Conduct focused enforcement for idling trucks; collaborate with the CSC to inform community members on how to report idling trucks; engage in community outreach on existing complaints/response systems to report idling trucks. | 5b Action 1 Goals: 1. Conduct, at minimum, quarterly idling sweeps and focused inspections for one calendar year, to be evaluated thereafter with community input. 2. Engage in two outreach events within the during the span of implementation of this CERP to inform community members how to report idling trucks. | 1. Number of idling sweeps conducted and results of idling sweeps. 2. Number of outreach events. | Enforcement; Collaboration; Public Information and Outreach | 1) 4 Sweeps in SBM 9/26/19 – 24 trucks, 0 stickers, 2 NOVs 11/10/19 – 11 trucks, 7 stickers, 0 NOVs 3/31/20 – 8 trucks, 2 stickers, 0 NOVs 6/4/20 – 18 trucks, 16 stickers, 0 NOVs 2) N/A, impacted by COVID-19 |  | X |  |  | N/A | N/A | N/A | 4 | 2 | 0 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (a) To date, staff has been conducting quarterly idling sweeps at targeted locations within the community. The locations are selected based on historical complaints, input gathered from the CSC, and other data sources. (b) The key benefit of conducting idling sweeps is a reduction in exposure to diesel particulate matter, particularly when trucks are found idling in residential areas or near schools. (c) None | a) N/A b) N/A c) N/A
Neighborhood Truck Traffic-Action 2 | 5b-6 | Reduce Emissions from Heavy-Duty Trucks Transiting the Community: Work with city or county on truck routes and truck parking; conduct outreach to truck owners and operators; identify incentive funding; support acceleration of zero-emission technology; target incentives to local small business; continue to develop Facility Based Mobile Source Measures-Indirect Source Rules; provide training on complaint reporting; participate in CARB rule development; and conduct focused enforcement. | 5b Action 2 Goals: 1. Organize one incentive outreach event (e.g., incentive fair, workshop) per year during the implementation period of this CERP, to be evaluated thereafter with community input. 2. Provide semiannual updates on incentive outreach events and CARB’s and South Coast AQMD’s rule development for truck regulations, and seek community input on progress. 3. Achieve emission reductions through mobile source incentives and statewide mobile source regulation measures as specified in Chapter 5a. | 1. Number of outreach events 2. Number of updates to the CSC. 3. (a) Emissions reductions; (b) Dollar amounts invested in incentives; and (c) Number of incentive projects implemented. | Incentives; Public Information and Outreach; Collaboration; Rules and Regulations; Enforcement | 1. In-person outreach events impacted by COVID-19. Outreach for Moyer funding was conducted via webcast and posted online. 2. Update to CSC / Outreach Event with CARB's TRUCRS group. 3. Reductions from incentives and regulation measures will be updated in future reports. |  | X |  |  | Outreach for Moyer funding opportunities provided via webcast (in lieu of public workshops due to COVID-19) posted on www.aqmd.gov/moyer | N/A | Webcasts only on www.aqmd.gov/moyer | N/A | N/A | N/A | N/A | N/A | See Tab 5d | See Tab 5d | See Tab 5d | N/A | N/A | N/A | N/A | N/A | a) Outreach for Moyer funding opportunities provided via webcast (in lieu of public workshops due to COVID-19) posted on www.aqmd.gov/moyer; Webcast information sent to subscribers via listserv; b) Incentives reduce NOX and DPM emissions from heavy-duty on-road vehicles, which will further decrease exposure to DAC communities; c) N/A | a) N/A b) N/A c) N/A
Neighborhood Truck Traffic-Action 3 | 5b-9 | Utilize Existing Traffic Information and New Technology to Identify Older Trucks for Incentive Programs: Gather existing traffic information; Explore the possibility of using ALPR system along with DMV data to identify trucks that travel through the community. | 5b Action 3 Goals: 1. Explore the possibility of using ALPR systems in this community and prioritize locations for ALPR systems based on community input. 2. Once ALPR systems have been deployed, provide ALPR data to the City and County to work towards truck routes. 3. Provide quarterly or biannual updates to the CSC on progress made to collect and use data from these systems. 4. Achieve emission reductions through mobile source incentives and statewide mobile source regulation measures as specified in Chapter 5a. 5. Conduct targeted outreach to provide information on incentive programs. | 1. Qualitative status update on the deployment of ALPR. 2. (a) Number and date of meetings with City and County; (b) Qualitative status update on truck routes that have undergone evaluation. 3. Number of updates to the CSC. 4. (a) Emissions reductions; (b) Dollar amounts invested in incentives; and (c) Number of incentive projects implemented. | Monitoring; Incentives; Public Information and Outreach; Collaboration | 1. Explore the possibility of using ALPR systems in this community and prioritize locations for ALPR systems based on community input. 2. Staff is working to develop policies that would protect privacy and govern the use of any ALPR system and are reviewing the implementation by both CARB and other air districts. 3. Update was given in October 2019. CERP estimated timeline is set for 2021. 4. Emission reductions from PEAQS/ALPR targeted incentive outreach TBD at a later time. 5. Targeted incentive outreach based on PEAQS/ALPR is dependent on deployment of PEAQS/ALPR system. | X |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1). Two 2). Three (email and webEx) 3). One (webinar) | 1). CARB 2). OpenALPR 3). Rekor Systems | N/A | (a) This action is scheduled to begin in 2021 in the estimated implementation timeline. ALPR systems have yet to be deployed. Staff is working to develop policies that would protect privacy and govern the use of any ALPR system and are reviewing the implementation by both CARB and other air districts. Staff has also solicited information from vendors and are reviewing to determine if those products/services meet project requirements. Data will be provided to the City and County to work towards establishing truck routes once it becomes available. (b) Exposure reductions anticipated once deployed. (c) N/A | (a) N/A (b) N/A (c) N/A

## 5c.DISTRICT Warehouse Onsite
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | DISTRICT STRATEGIES Chapter 5c-Warehouse On-Site Emissions | DISTRICT GOALS Goals for Each Strategy in Chapter 5c of San Bernardino/Muscoy CERP | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Warehouse On-Site Emissions-Action 1 | 5c-3 | Conduct Outreach to Local Governments to Encourage Avoidance of Air Quality Impacts from New Warehouse Development: Work with the city and county to enhance land use policies (e.g., development standards) that reduce residents’ exposure to emissions from old diesel trucks stopping at warehouse facilities (e.g., buffer zones, warehouse design, truck routes, green infrastructure, community outreach, and development of Air Quality Mitigation/ Community Benefit Funds). | 5c Action 1 Goals: 1. Provide technical input to local land use agencies on reducing air quality impacts from warehouse land uses, (e.g., during general plan and community plan updates). | 1. (a) Number of meetings with other agencies/organizations; (b) List of any specific plan updates. | Collaboration; Public Information and Outreach; Exposure Reduction | 1. Staff has reached out to City and County staff to make initial contact to establish a partnership aimed at providing technical input to reduce air quality impacts from warehouse land uses. Additionally, staff reviews and provides project-specific comment letters on new warehouse developments in, or near SBM, encouraging implementation of zero-emission technology, warehouse configuration aimed at reducing truck travel near sensitive receptors, and other measures to avoid or mitigate air quality impacts. |  | X |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | a) N/A b) N/A c) N/A | a) N/A b) N/A c) N/A
Warehouse On-Site Emissions-Action 2 | 5c-4 | Develop Proposed Indirect Source Rule (ISR) for Warehouses: Continue developing proposed Indirect Source Rule (ISR) for warehouses. | 5c Action 2 Goals: 1. Provide quarterly updates to CSC on rule development for warehouses. 2. Bring proposed ISR for warehouses for Board consideration. | 1. Number of updates to the CSC. 2. Dates for regulatory actions. 3. Number of outreach events. | Regulation; Public Information and Outreach; Collaboration; Exposure reduction | 1. Updates provided at January and May 2020 CSC meetings 2. Warehouse ISR public hearing anticipated first quarter 2021. |  | X |  |  | Working Groups/Board Updates | 5 post CERP adoption (4 WGs, 1 update to MS cmte) | Diamond Bar | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-11-13 | Expected first quarter 2021 | 20+ | CARB, Southern California Public Power Authority, Energy Commission, Public Utilities Commission, SBCTA | South Coast AQMD Governign Board is expected to consider this project in the first quarter of 2021. | (a) N/A (b) N/A (c) N/A | (a & b) Rule adoption moved to 1st quarter 2021 in response to COVID-19. Public hearing dates were delayed to allow more time to work with stakeholders and to incorporate modifications to the rulemaking process. (c) No emission reduction targets in CERP for Warehouse ISR.
Warehouse On-Site Emissions-Action 3 | 5c-5 | Promote Installation of Infrastructure Needed to Support Zero-Emission Vehicles and Equipment: Collaborate with local governments, utilities, and local and state entities to promote the installation of fueling infrastructure needed to support zero-emission trucks/vehicles, transport refrigeration units and cargo handling equipment. | 5c Action 3 Goals: 1. South Coast AQMD and SCE will provide outreach to all 43 existing warehouses within the San Bernardino, Muscoy community to encourage installation of infrastructure needed to support zero-emission vehicles and equipment. 2. Engage in outreach to any new/planned future sites (and project partners) and determine feasibility to install zero-emission electric infrastructure, serving potential zero-emission vehicles and/or equipment in the San Bernardino, Muscoy community. 3. South Coast AQMD and SCE will track adoption of zero-emission infrastructure and provide updates to the CSC. 4. Identify sites for installation of electrical infrastructure. | 1. Number of outreach events for existing warehouses. 2. Number of outreach events for new/planned warehouses. 3. Number of updates to the CSC. 4. List of sites for installation of electrical infrastructure. | Public Information and Outreach; Collaboration | 1. Initiated collaboration with SCE for warehouse zero emission infrastructure outreach 2. Staff is evaluating different outreach opportunities for this goal. 3. Staff has initiated collaboration with SCE for other commitments, and will continue to do so for this as well. 4. This effort is ongoing. |  | X |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | a) N/A b) Exposure reduction is anticipated. c) N/A | a) N/A b) N/A c) N/A

## 5d.DISTRICT Omnitrans
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in Plan | Page # in Plan | DISTRICT STRATEGIES Chapter 5d-Omnitrans Bus Yard | DISTRICT GOALS Goals for Each Strategy in Chapter 5d of San Bernardino/Muscoy Plan | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Omnitrans Bus Yard-Action 1 | 5d-2 | Conduct Air Monitoring to Identify the Composition and Level of Emissions Near the Omnitrans Bus Yard: Air measurements near the Omnitrans Bus Yard; identify potential sources; conduct appropriate follow-up investigations. | 5d Action 1 Goals: 1. Conduct measurements near Omnitrans to identify potential sources of emissions. 2. Provide quarterly or semiannual updates to the CSC on air measurement data results and information collected. | 1. Qualitative status update on air measurement results. 2. Number of updates to the CSC. | Air Monitoring; Enforcement | 1. June to December 2019 – Individual air measurements taken (monitoring investigations are ongoing) 2. Updates provided at October 2019 CSC meeting |  | X |  |  | N/A | N/A | N/A | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (a) Methane measurements were conducted on five different weekdays between June and December 2019 with South Coast AQMD’s mobile platform in the SBM community and around the Omnitrans bus yard. Aerodyne Mobile Laboratory (AML) (contractor) visited the area surrounding the bus yard on five different days to measure ambient air quality, and sample stormdrains and manholes in the area . OCE conducted surveillance and an inspection of the Omnitrans facility in August 2019, where a Notice to Comply was issued and has since been resolved. While the findings did not conclude the source of the methane that was detected by Monitoring, the facility was ensured to be in compliance with rules and regulations. Further, a second Omnitrans facility in SBM was inspected in January 2020, in which the facility was in compliance with rules and regulations. (b) TBD (c) None | a) N/A b) N/A c) N/A
Omnitrans Bus Yard-Action 2 | 5d-3 | Support Omnitrans’s Transition to Zero-Emission Buses: Support Omnitrans’s efforts to accelerate the deployment of zero-emission buses and supporting infrastructure (e.g., letters of support); provide information on incentive opportunities. | 5d Action 2 Goals: 1. Develop proposals and apply for grants that accelerate the deployment of zero emission buses and electric vehicle chargers, in collaboration with Omnitrans. 2. Replace the total fleet with electric buses, subject to availability of resources. | 1. Dollar amounts invested in incentives 2. (a) Number of incentive projects implemented; and (b) Emissions reductions from incentive projects | Public Information and Outreach; Collaboration | 1. May 2019 and March 2020 – Provided letter of support for Omnitrans' grant proposals 2. Outreach for Moyer funding opportunities provided via webcast (in lieu of public workshops in the community due to COVID-19) posted on www.aqmd.gov/moyer. |  | X |  |  | Outreach for Moyer funding opportunities provided via webcast (in lieu of public workshops due to COVID-19) posted on www.aqmd.gov/moyer | N/A | Webcasts only on www.aqmd.gov/moyer | N/A | N/A | N/A | N/A | N/A | 0.3M | 21 (Low-NOX) | 0.6 TPY (NOX) 0 TPY (ROG) 0 TPY (DPM) | N/A | N/A | N/A | N/A |  | a) Omnitrans applied for grant proposals. b) Replacing fleet with cleaner technology will result in emission reductions. c) N/A | a) N/A b) N/A c) N/A

## 5e.DISTRICT Railyards
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in Plan | Page # in Plan | DISTRICT STRATEGIES Chapter 5e-Railyards | DISTRICT GOALS Goals for Each Strategy in Chapter 5e of San Bernardino/Muscoy Plan | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Railyards-Action 1 | 5e-5 | Reduce Emissions from Railyards: Pursue development of indirect source requirements; work with CARB to develop new requirements; work with local utilities and state agencies to encourage ZE infrastructure installation; continue to support CARB's US EPA petition for new national locomotive emission standards; work with BNSF railyard to replace diesel fueled equipment with cleaner technologies; conduct air measurements; and use emissions inventory and air monitoring information to identify possible emissions reductions. | 5e Action 1 Goals: 1. Provide semiannual updates and engage the CSC on new requirements being developed by CARB and South Coast AQMD 2. Provide quarterly or annual updates to the CSC on air monitoring results. 3. Replace two line haul and two switcher locomotives at the BNSF railyard through incentive funding programs. 4. Achieve emission reductions through mobile source incentives and statewide mobile source regulation measures as specified in Chapter 5a. | 1. Number of updates to the CSC on railyard requirements. 2. Number of updates to the CSC on air monitoring results. 3. (a) Dollar amounts invested in incentives; (b) Number of incentive projects implemented; and (c) Emissions reductions from incentive projects. 4. Emissions reductions from mobile source regulation measures. | Rules and Regulations; Incentives; Collaboration; Air Monitoring | 1. Provide semiannual updates and engage the CSC on new requirements being developed by CARB and South Coast AQMD 2. Provide quarterly or annual updates to the CSC on air monitoring results. 3. Replace two line haul and two switcher locomotives at the BNSF railyard through incentive funding programs. 4. Achieve emission reductions through mobile source incentives and statewide mobile source regulation measures as specified in Chapter 5a. |  | X |  |  | Community Meetings/Board Updates | 5 post CERP Adoption | Diamond Bar, Boyle Heights, San Bernardino | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30+ | CARB, High Speed Rail Authority, Energy Commission, Public Utilities Commission, Southern California Public Power Authority | -Joint CARB/South Coast AQMD staff update to Governing Board 4/3/20 -Staff updates to Mobile Source Commmittee 3/20/20 and 9/20/19 | Regulations under development. | (a & b) Rule adoption moved from December 2020 to 2nd quarter 2021 due to COVID-19-related delays (staffing and outreach). (c) No emission reduction targets in CERP for Railyard ISR.

## 5f.DISTRICT Concrete-Asphalt
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in Plan | Page # in Plan | DISTRICT STRATEGIES Chapter 5f-Concrete Batch Plants, Asphalt, and Aggregate Plants | DISTRICT GOALS Goals for Each Strategy in Chapter 5f of San Bernardino/Muscoy Plan | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Concrete Batch Plants, Asphalt, and Aggregate Plants-Action 1 | 5f-4 | Reduce Fugitive Dust, Particulate Matter (PM10) and Odors from Concrete Batch, Asphalt Batch, and Rock and Aggregate Plants: Provide public outreach information for the community on Rules 402, 403, 1155, and 1157 requirements; conduct focused air monitoring. | 5f Action 1 Goals: 1. Hold a public outreach event for the first year of the implementation period to explain the requirements of Rules 402, 403, 1155, and 1157, and the South Coast AQMD’s complaint process. If necessary, determine if additional annual outreach events are needed. 2. Provide quarterly or semiannual updates to the CSC on enforcement activities. 3. Conduct air monitoring near Robertson’s Ready Mix and Vulcan Materials in year one. | 1. Number of outreach events 2. Number of updates to the CSC. 3. Qualitative status update on air measurement results. | Public Information and Outreach; Air Monitoring; Enforcement | 1. In-person outreach events were impacted by COVID-19 2. Periodic updates will be given at CSC meetings 3. A combination of mobile and fixed air monitoring is employed to address this air quality priority. Mobile surveys were conducted near the facilities, fixed monitoring for PM10 and hexavalent chromium were conducted upwind and downwind of the facilities. |  | X |  |  | N/A | N/A | N/A | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | a) Inspections have been conducted at three asphalt/cement/aggregate plants, however the "report back" to the CSC was delayed as a result of the COVID-19 pandemic. The report back for asphalt plants can be completed in the second half of 2020. b) The health benefits of conducting inspections at these facilities is in the verification that they are complying with applicable rules and regulations. Compliance results in lower emissions and exposures. c) N/A | a) N/A b) N/A c) N/A

## 5g.DISTRICT Exposure Reduction
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
South Coast AQMD: San Bernardino/Muscoy
[6 empty] | QUALITATIVE STATUS UPDATE | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in Plan | Page # in Plan | DISTRICT STRATEGIES Chapter 5g-Exposure Reduction for Sensitive Populations in Schools, Childcare Centers, and Homes | DISTRICT GOALS Goals for Each Strategy in Chapter 5g of San Bernardino/Muscoy Plan | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
Exposure Reduction-Action 1 | 5g-5 | Reduce Exposure to Harmful Air Pollutants through Public Outreach: Provide air quality related programs to schools (like EJCP Clean Air Ranger Education (CARE) and Why Air Quality Matters (WHAM)); partner with SB County public health department to provide information on how to receive air quality advisories and reduce exposure to air pollution; partner with community based organizations to share information at schools on asthma programs; partner with Safe Routes to School to provide information on programs such as walkability and active transportation; work with appropriate parties to negotiate access to conduct school-based air monitoring. | 5g Action 1 Goals: 1. Participate in six public outreach events (e.g., health fairs, community events) during the implementation period of this CERP and provide air quality related information to reduce exposure. 2. Provide information relating to air quality effects on young children and reducing exposure to facilities where children are located (e.g. preschools, childcare centers, charter schools, etc.). Outreach will be prioritized based on CSC input during the implementation of the CERP. Present CARE and WHAM programs in at least two schools during the implementation period of this CERP, with the possibility of continuing for up to three years. 3. Collaborate with community-based organizations (e.g., ChICCCAA, CCAEJ) and co-engage in outreach meetings. 4. Conduct school-based air monitoring. | 1. Number of outreach events 2. Number of updates to the CSC. 3. Number of meetings with other agencies/organizations. 4. Qualitative status update on air measurement results at schools. | Public Information and Outreach; Collaboration; Air Monitoring | 1. COVID-19 impacted in-person outreach events. The May 2020 CSC meeting included a CSC member presentation on Safe Routes to Schools. 2. Three schools in SBM signed up for WHAM program. 3. CSC Updates / CSC Presentation - Safe Routes to Schools 4. Working with CSC members to establish a sensor netwok for SBM community. |  | X |  |  | Safe Routes to Schools Presentation | 1 | Virtual - Zoom | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | a) N/A b) N/A c) N/A | a) N/A b) N/A c) N/A
Exposure Reduction-Action 2 | 5g-7 | Reduce Exposure to Harmful Air Pollutants at Schools, Childcare Centers, and Community Centers: Work with appropriate entities to implement the installation of high efficiency air filtration systems; work with the community to prioritize schools, childcare centers, and community centers near truck routes, railyards, and concrete batch plants; work with appropriate agencies to replace filters at schools with air filtration systems and installation at schools without these systems | 5g Action 2 Goals: 1. Installation of air filtration systems in schools, childcare centers, and community centers with priority given to schools located in areas with high diesel PM levels and close to facilities identified as a priority by the CSC. | 1. Number of air filtration systems installed. | Exposure Reduction | 1. Criteria for Air Filtration Systems Activity was conducted at the CSC Quarterly Update Meeting 1 in January, 2020. Input obtained from the CSC and the public was used to establish criteria for prioritization of schools. The resulting List of Prioritized Schools was published on the website and to the CSC. South Coast AQMD requested CAPP funds from CARB to begin installation at the first ten schools on the list. Funding was approved by CARB. |  | X |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1. One 2. Multiple | 1. San Bernardino City Unified School District (SBCUSD) School Board 2. SBCUSD maintenance staff | N/A | a) Criteria for Air Filtration Systems Activity was conducted at the CSC Quarterly Update Meeting 1 in January, 2020. Input obtained from the CSC and the public was used to establish criteria for prioritization of schools. The resulting List of Prioritized Schools was published on the website and to the CSC. South Coast AQMD requested CAPP funds from CARB to begin installation at the first ten schools on the list. b) High-efficiency air filtration systems have been shown to reduce concentrations of particulate matter less than or equal to 2.5 microns (PM2.5), including diesel particulate matter (DPM), by 87% to 96% on average. c) N/A | a) N/A b) N/A c) N/A
Exposure Reduction-Action 3 | 5g-8 | Reduce Exposure to Harmful Air Pollutants at Homes: Identify new or existing technologies, programs, and funding sources that can provide the most effective air filtration systems in homes. | 5g Action 3 Goals: 1. Partner with appropriate entities to determine new or existing programs that can provide home filtration systems and weatherization. 2. If funding or programs become available, share information with CSC. | 1. Number of meetings with other agencies/organizations. 2. Number of updates to the CSC. | Exposure Reduction; Incentives; Public Information and Outreach | 1. Staff has conducted four meetings with contractors and community members to develop a plan for a residential air filtration pilot study, funded by a Supplemental Environmental Project (SEP). 2.Provided update to CSC regarding Residential Air Filtration Pilot Study at Quarterly CSC Meeting 2 in May, 2020. |  | X |  |  | Quarterly CSC Meeting 2 | 1 | Virtual Zoom platform | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4 | Contractor(s) Community Members; CARB staff | Two CARB Supplemental Environmental Projects (SEP) required action by the South Coast AQMD Governing Board and were approved in the April 2020 Governing Board Meeting minutes. | a) In April 2020, the South Coast AQMD Board approved two CARB Supplemental Environmental Projects to initiate a residential air filtration pilot study in EJ communities. This study will inform future residential air filtration deployment projects by establishing protocols for monitoring and optimal configuration. An update was provided to the CSC at the CSC Quarterly Update Meeting 2 in May, 2020. (b) High-efficiency air filtration systems have been shown to reduce concentrations of particulate matter less than or equal to 2.5 microns (PM2.5), including diesel particulate matter (DPM), by 87% to 96% on average. (c) There are no relevant land use or permitting issues for this strategy. | a) N/A b) N/A c) N/A
Exposure Reduction-Action 4 | 5g-9 | Increase Green Space in Areas Where People Spend Time: Identify new or existing sources or programs that can provide funding for tree planting. If funding or programs become available, share information with CSC members. | 5g Action 4 Goals: 1. Partner with other entities to determine new or existing sources or programs that can provide funding for tree planting. If funding or programs are available, share information with CSC members. | 1. Number of meetings with other agencies/organizations. Number of updates to the CSC. | Public Information and Outreach; Collaboration | 1. Staff has reached out to other entities to provide information and offer letters of support on tree planting programs, such as the Urban Greening Grant Program administered by the California Natural Resources Agency. Staff is continuing to seek new or existing sources or programs that can provide funding for tree planting. |  | X |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | City of San Bernardino, San Bernardino County, Safe Routes Partnership | N/A | (a) Staff has reached out to other entities to provide information and offer letters of support on tree planting programs, such as the Urban Greening Grant Program administered by the California Natural Resources Agency. Staff is continuing to seek new or existing sources or programs that can provide funding for tree planting. (b) As a proximity-based buffer, green spaces can reduce ambient PM concentrations, enhances atmospheric CO2 removal, and encourages vertical dispersion of pollutant emissions instead of horizontal. (c) Land use or permitting issues relating to tree planting are anticipated but have not been identified at this time. | a) N/A b) N/A c) N/A
Exposure Reduction-Action 5 | 5g-9 | Replace Older School Buses: Identify new or existing sources or programs that can provide funding for alternative fueled school buses | 5g Action 5 Goals: 1. Partner with other entities to determine new or existing sources or programs that can provide funding for near zero or zero-emission school buses. | 1. Number of meetings with other agencies/organizations. | Public Information and Outreach | 1. This action is scheduled to begin mid-2020 in the estimated implementation timeline. Staff is continuing to seek new or existing sources or programs that can provide funding for near zero or zero-emission school buses. |  | X |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (a) This action is scheduled to begin mid-2020 in the estimated implementation timeline. Staff is continuing to seek new or existing sources or programs that can provide funding for near zero or zero-emission school buses. (b) Diesel bus emissions contribute to both regional and local pollutants that impact the community. Encouraging the deployment and complete fleet turnover would decrease regional NOx and local concentrations of diesel particulate matter. Reducing each of these pollutants would directly benefit the community, reducing acute respiratory distress and inflammation, and chronic exacerbation of respiratory diseases and/or development of cancer. (c) There are no relevant land use or permitting issues for this strategy. | a) N/A b) N/A c) N/A