## README
Annual Progress Report for AB 617 Community Emissions Reduction Programs
DRAFT Data Collection Template - Calexico/El Centro/Heber
Purpose: Use this Excel spreadsheet template to provide status updates for each strategy, as identified in your community emissions reduction program. Attach this spreadsheet to the Microsoft Word template that describes overall progress for your program. This spreadsheet includes the following tabs:
CARB Metrics: This workbook summarizes the metrics CARB will use to track progress of statewide strategies in the "Imperial County Year 1 Community Emissions Reduction Program Plan for the El Centro-Heber-Calexico Corridor" (Imperial Program). The CARB strategies included in the Imperial Program are grouped into three categories with a separate tab for each: Regulatory, Enforcement, and Guidance. The CARB Incentives tab provides metrics for incentive projects that are located in the El Centro-Heber-Calexico corridor and are funded by a statewide incentive program.
1. CARB Regulatory Metrics: | CARB regulatory metrics track CARB's regulatory development process for strategies identified in the Imperial Program. These metrics are cumulative since the initiation of regulatory development.
2. CARB Enforcement Metrics: | CARB enforcement metrics are cumulative since 2019.
3. CARB Guidance Metrics: | CARB guidance metrics track CARB's guidance development process and are cumulative since the initiation of guidance development.
4. CARB Incentive Metrics: | CARB incentive metrics are cumulative since 2017.
DISTRICT Metrics: This workbook also summarizes the metrics that the Imperial County Air Pollution Control District (ICAPCD) will use to track progress of district strategies included in the "Imperial County Year 1 Community Emissions Reduction Program Plan for the El Centro-Heber-Calexico Corridor"(Imperial Program). The district metrics are grouped into four categories with a separate tab for each: Regulatory, Incentives, Enforcement, and Coordination.
5. DISTRICT Regulatory Metrics: | DISTRICT regulatory metrics track the progress of strategies related to district rules or permitting.
6. DISTRICT Enforcement Metrics: | DISTRICT enforcement metrics track the progress of strategies related to enforcement, including associated outreach/training events.
7. DISTRICT Coordination Metrics: | DISTRICT coordination metrics track the progress of strategies related to coordination with other groups (e.g., government agencies, schools, working groups, etc.), , including associated outreach/training events.
8. DISTRICT Incentive Metrics: | DISTRICT incentive metrics track the progress of strategies related to incentive projects, including associated outreach events.
CARB Emissions Benefit Caveats: • CARB adopted the Ocean-Going Vessels At Berth Amendment on August 27, 2020. Benefits for this regulation are shown here as the community emission inventory (May-June 2020) did not inlcude the benefits of this regualtion in future years 2024/25 and 2029/30. • CARB adopted the Advanced Clean Truck on June 25, 2020. Benefits for this regulation are shown here as the year-1 community emission inventories did not inlcude this regulation in the baseline projections for 2024/25 and 2029/30. • CARB adopted the Heavy-Duty Engine and Vehicle Omnibus regulation (previosuly HD Low-NOx Engine Standard) on August 27, 2020. Benefits for this regulation are shown here as the community emission inventories (May-June 2020) did not inlcude this regulation in the baseline projections for 2024/25 and 2029/30. • TRU Regulation was not included in the benefits calculation last year. Preliminary reg inventory data was not available until mid 2021. We might want to loop back with TTD on the estimated benefits.
REFERENCES
CARB Community Air Protection Blueprint, October 2018, Appendix C, pages C-38 to C-40
https://ww2.arb.ca.gov/our-work/programs/community-air-protection-program/community-air-protection-blueprint
Imperial County Year 1 Community Emissions Reduction Program Plan for the El Centro-Heber-Calexico Corridor, October 8, 2019
https://c1b3e492-1448-4e62-b7f8-7aaf61550a90.filesusr.com/ugd/99eb03_080a305618f5453cb0c69272eb622946.pdf
CARB “El Centro - Heber - Calexico Community Emissions Reduction Program Plan Staff Report”, December 18, 2019
https://ww2.arb.ca.gov/resources/documents/el-centro-heber-calexico-community-emissions-reduction-program-plan-staff
CARB Board Resolution 20-1, January 15, 2020
https://ww2.arb.ca.gov/board-resolutions-2020
QUESTIONS? Send an email to: | CommunityAir@arb.ca.gov
Date last modified: | Version | CARB Authors
2021-09-22 | 2 | Jeremy Herbert; Hanjiro Ambrose
Policy metrics vintage - June 16, 2021
Incentive metrics vintage - TBD
Enforcement metrics vintage - TBD
Guidance metrics vintage - June 16, 2021
CARB-Air District Discussion Only ¦ Draft Deliberative

## 1.CARB Regulatory
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
Imperial County APCD: Calexico/El Centro/Heber
|  |  |  | Outreach |  |  | Non-Regulatory Documents |  |  |  | Regulatory Process Milestones | [5 empty] | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable) |  | Community Criteria and Toxics Emissions Forecasted Baseline Emissions (tpy) (2024) | [8 empty] | Community Criteria and Toxics Emissions Draft Emissions Reductions, As Available (tpy) (2024) | [8 empty] | Community Criteria and Toxics Emissions Final Emissions Reductions (tpy) (2024)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | CARB Regulation | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Non-Regulatory Document(s) (Text) | Draft Document Release(s) (Date) | Final Document Release(s) (Date) | Workshops/Webinars | Release of 45 day or 60 day package | First Board hearing | Potential 15 day changes | Final Board hearing | OAL approval | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM
R-2 | 4-6 | CARB would consider expanded California-specific standards for new light-duty vehicles, impacting 2026 and later model year vehicles, to increase the number of new zero emission and plug-in hybrid electric vehicles sold in California and increase the stringency of fleet-wide emission standards for greenhouse gases and criteria pollutants. | Advanced Clean Cars 2 | 3 | 1017 | Virtual | 5 | 1. Workshop Presentation 2. Workshop Presentation 3. Proposed Puff Equation: Evaporative Emissions 4. Proposed 3 Bin Moving Average Window Method for Chassis Certified Medium Duty Vehicles 5. Draft ZEV Data Parameters |  | 1. 9/24/20 2. 5/19/21 3. 5/19/21 4. 5/19/21 5. 5/26/21 | 2 | [5 empty] | CARB staff will host at least two additional workshops in 2021 (in the summer and fall) on the Advanced Clean Cars II rulemaking before the targeted June 2022 board hearing. | The Advanced Clean Cars 2 Regulation is tentatively scheduled for June 2022. | a) CARB has been developing Advanced Clean Cars II since 2017 and expects board adoption in 2022, with most provisions taking effect as soon as model year 2026. b) Light duty vehicles continue to be a significant contributor of greenhouse gases to the California inventory. The proposed regulation will result in significant decreases in greenhouse gas emissions. Additionally, increased ZEVs and further emission controls for combustion vehicles will contribute to long term criteria pollutant reductions. c) An indirect impact of a larger market share of ZEVs resulting from these regulations will be the associated development of charging and hydrogen infrastructure to fuel these vehicles. Constructing this infrastructure requires permits and may increase development outside of existing paved areas, for instance separate from current gasoline fueling stations.
R-2 | 4-6 | CARB is working through a public process to develop and consider proposals for new approaches and strategies that may transition to zero emission technology those truck fleets that operate in urban centers, have stop and go driving cycles, and are centrally maintained and fueled | Advanced Clean Trucks | 13 | 516 | Sacramento, Webcast | 4 | 1. Factsheet 2. ACT Truck Market Segment Analysis 3. Total Cost of Ownership Discussion Document 4. Battery-Electric Truck and Bus Energy Efficiency Compared to Conventional Diesel Vehicles |  | 1. 2/7/19 2. 2/25/19 3. 2/25/19 4. 5/18 | 12 | 2019-10-22 | 2019-12-12 | 2020-05-01 | 2020-06-25 | 2021-03-15 |  | The Advanced Clean Trucks first heard on 12/12/19. The 15-Day changes was posted 4/28/20. Comments close 5/28/20. The Advanced Clean Trucks was adopted on 6/25/20. The Advanced Clean Trucks was approved by OAL 3/15/21. | a) CARB has been developing the Advanced Clean Trucks regulation since 2016, expects adoption in 2020 and will begin implementation in 2024. b) As a result of the Advanced Clean Trucks regulation, from 2020 to 2040, NOx and PM2.5 emissions are estimated to be cumulatively reduced by 58,313 tons and 1916 tons, respectively. From 2020 to 2040, the Proposed Modifications are expected to reduce GHG emissions by a cumulative 17.3 MMT CO2e. The estimated total statewide health benefits derived from criteria emission reductions are estimated to be $8.9 billion from 2020 to 2040. From 2020 to 2040, statewide avoided premature deaths are estimated to be 943, avoided hospitalizations for cardiovascular illness are estimated to be 148, avoided hospitalizations for respiratory illnesses are estimated to be 177, and avoided ER visits are estimated to be 453. c) None, this is a manufacturer sales requirement. CEQA impacts include increased construction of EVSE infrastructure. |  | 69.3634 | 0 |  | 1.5597 |  |  |  |  | 0.52582 | 0.18502 | 0 |  | 0.0041262 |  |  |  |  | 0.0017369
R-2 | 4-6 | When emissions control systems are not operating correctly, in-use emissions can increase. CARB’s current inspection programs include the roadside Heavy-Duty Vehicle Inspection Program and the fleet Periodic Smoke Inspection Program. These regulations require heavy-duty vehicles operating in California to be inspected for excessive smoke and tampering. In July 2018, CARB approved amendments to the Heavy-Duty Vehicle Inspection Program and the Periodic Smoke Inspection Program to reduce the smoke opacity limits to levels more appropriate for today’s modern engine technology. CARB is now exploring the development of a more comprehensive heavy-duty inspection and maintenance program which would help ensure all vehicle emissions control systems are adequately maintained throughout the vehicles’ operating lives | Heavy-Duty Inspection & Maintenance | 13 | 2456 | Sacramento, Teleconference, Webcast, Webinar | 1 | 1. Draft Proposed HD I/M Regulatory Text Document | 2021-03-01 |  | 13 |  | 2021-12-09 |  |  |  | Staff is currently revising the Draft Proposed HD I/M Regulatory Text Document and expects to release it in the July timeframe. Discussions will continue with stakeholders to incorporate additional feedback necessary to finalize the proposed regulation before its official release in October 2021 for public comment. | This strategy requires CARB action during at least one board hearing. | a) CARB staff has conducted public workshops in 2019, 2020, and 2021, and plans at least one additional workshop or workgroup meeting for later this summer (2021) as program development continues. Staff has also conducted 9 focused HD I/M workgroup meetings to date with industry experts, environmental organizations, trucking associations, fleet representatives, and other governmental agencies. Staff will continue to engage with all interested stakeholders to develop and finalize the proposed regulation. b) HD I/M is a key measure in California's State Implementation Plan statewide strategy and one of the largest proposed near-term NOx reduction measures to meet the South Coast’s 2023 ozone attainment deadline and San Joaquin Valley's 2024 PM 2.5 attainment deadline. Staff is currently performing analyses to update emissions reduction estimates and health exposure reduction benefits. c) Coordinating with Caltrans on permitting for placement of RSDs, ALPRs, and potential OBD-data collection kiosks when sited on public roadways (RSDs, ALPRs) or at rest-stops or other Caltrans-owned land (for kiosks). There are no major land use or permitting issues for HD I/M and no expected CEQA impacts. | a) When included as a critical measure in the 2016 Mobile Source Plan and the 2016 Statewide SIP Strategy, staff anticipated that a comprehensive HD I/M program could be proposed to the Board in 2020. Recognizing that such a program would provide significant emission reductions and health benefits, the Legislature proposed and ultimately adopted critical legislation in 2019 (SB 210; Leyva) to provide CARB authority to develop/implement a robust HD I/M program unlike any other in the nation. The timing of the legislative process necessitated moving the Board date to the 2021 timeframe. b) CARB staff is scheduled to present a regulatory HD I/M program to the Board for its consideration at the December 9-10, 2021, Board meeting. c) With HD IM program implementation expected to be phased-in starting in 2023, the HD I/M program is expected to be on track to achieve near-term reductions in 2023/2024 at the community level. | 74.5775 | 0 |  | 0.53539 |  |  |  |  | 0.55958 | 18.8171 | 0 |  | 0.13267 |  |  |  |  | 0.13866
R-2 | 4-6 | This measure would establish lower NOX standards and associated test procedures for model year 2022 and subsequent model year medium-duty and heavy-duty engines. CARB is in the process of evaluating the technical feasibility of this measure. | Heavy-Duty "Omnibus" Low NOx Rulemaking | 14 | 1060 | Diamond Bar, Sacramento, GoToMeeting, Webcast | 1 | 1. CARB Staff White Paper: California Air Resources Board Staff Current Assessment of the Technical Feasibility of Lower NOx Standards and Associated Test Procedures for 2022 and Subsequent Model Year Medium-Duty and Heavy-Duty Diesel Engines |  | 2019-04-18 | 14 | 2020-06-23 | 2020-08-27 | 2021-05-05 |  |  |  | The Heavy-Duty Engine and Vehicle Omnibus Regulation and Associated Amendments will have the first board hearing 8/27/19. The 60-Day Notice of Proposed Amendments changes was posted 6/23/20. Comments close 8/25/20. | a) Research contracts, workgroup and workshops, met engine manufacturers, component manufacturers, US EPA, outreach. b) NOx is a precursor to ozone and secondary PM formation. Californians would benefit from reduced emergency room and doctor’s office visits for asthma, reduced hospitalizations for worsened heart diseases, and reduced premature death. This in turn would result in reduced asthma-related school absences, reduced sick days off from work, reduced health care costs, and increased economic productivity. c) None |  | 76.0197 | 0 |  | 0 |  |  |  |  | 0 | 0.19938 | 0 |  | 0 |  |  |  |  | 0
R-2 | 4-6 | In 2020, CARB will consider new standards for small off-road engines (SORE), which are spark-ignition engines rated at or below 19 kilowatts and used primarily for lawn, garden, and other outdoor power equipment | Small Off-Road Engine Amendment | 6 | 726 | Sacramento, Webinar | 13 | 1. Potential Amendments to Evaporative Emission Regulations 2. Potential Amendments to Exhaust Emission Regulations 3. Potential Amendments to TP-901 4. Potential Amendments to TP-902 5. Potential Amendments to CP-902 6. Potential Amendments to Part 1054 7. Potential Amendments to Part 1065 8. Potential Evaporative Emission Regulation Amendments 9. Potential Exhaust Emission Regulation Amendments 10. Potential Amendments to TP-901 11. Potential Amendments to TP-902 12. Potential Amendments to CP-902 13. Small Off-Road Engines Fact Sheet |  | 1. 3/24/21 2. 3/24/21 3. 3/24/21 4. 3/24/21 5. 3/24/21 6. 3/24/21 7. 3/24/21 8. 6/9/20 9. 6/9/20 10. 6/9/20 11. 6/9/20 12. 6/9/20 13. 2/4/19 | 6 | [7 empty] | a) CARB has conducted three public workshops on the potential amendments in September 2019, June 2020, and March 2021, and expects to take the rulemaking package to the Board in 2021 or 2022. If the Board adopts the proposed regulation and OAL approves it, CARB anticipates it will begin implementation of the regulation in 2024 or 2025. b) Premature cardiopulmonary mortality cases avoided: 892 Hospitalizations for cardiovascular illness avoided: 142 Hospitalizations for acute respiratory illness avoided: 169 Emergency room visits avoided: 439 (These are based on regulatory scenario presented in the March 2021 workshop. Changes may be made before ISOR is published.) c) None |  | 129.5745 | 60.1623 |  | 5.1107 |  |  |  |  | 3.5504 | 7.2347 | 2.1428 |  | 0.11316 |  |  |  |  | 0.092307
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 2.CARB Enforcement
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
Imperial County APCD: Calexico/El Centro/Heber
|  |  |  | Outreach |  |  | Inspections |  |  |  | Coordination |  |  |  |  | SB 1 Implementation |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | Agency | Events within Community (Qty) | Attendees (Qty) | Locations of Events (Text) | Complaint Inspections (Qty) | CERP Inspections (Qty) | NOVs (Qty) | Compliance Rate (%) | Agencies Engaged (Qty) | Names of Agencies Engaged (Text) | Meetings (Qty) | Resulting Actions (Qty) | Description of Resulting Actions (Text) | Statewide Vehicle Turnover (Qty) | Community Registration Holds (Qty) | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
E-10 | 5-18 | District is proposing to work in conjunction with CARB to identify enforcement strategies within CARB's current regulatory programs that could benefit the Corridor. | CARB & ICAPCD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | CARB Enforcement and the Imperial County Air Pollution Control District (ICAPCD) have begun discussions regarding idling reduction and coordinating enforcement efforts in the corridor.
CARB E1 | 5-19 | Increase frequency of CARB compliance inspections with guidance from the Steering Committee: CARB will collaborate with the Steering Committee co-chairs to work with the Steering Committee members to actively enhance CARB enforcement activities through a combination of improved complaint reporting, more focused inspections, and report-back meetings to update the Steering Committee on the status of CARB inspections and to obtain additional areas of mobile source concern. CARB will work with the co-chairs to meet annually with the Steering Committee in order to prioritize CARB enforcement strategies and identify possible locations where non-compliant vehicles are present. CARB will report back to the Community with the number of CARB inspections performed, mapped locations of the enforcement, and the number of citations and/or Notices of Violations issued. | CARB | N/A | N/A | N/A | 18 HDDV inspections: 1 enforcement action taken, 17 under investigation | 626 HDDV program inspections (does not include idling) within community boundaries | 109 HDDV violations within community boundaries | 83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | CARB Enforcement prepared a report for 2019 activities, but is still pending release and comments from the community members and CSC. CARB is working on a platform to host annual reports.
CARB E2 | 5-19 | Coordinate and conduct inspections of stationary sources with ICAPCD staff when assistance is requested by the District: Based on Steering Committee input and upon evaluation of concerns, the District can request assistance from CARB and coordinate joint inspections of stationary | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E3 | 5-19 | Achieving Compliance with the Truck and Bus Regulation via Senate Bill 1: In April 2017, the Governor signed Senate Bill 1 (SB 1) into law, which included a provision that, beginning in 2020, a vehicle must demonstrate compliance with the STB regulation before it can be registered with the Department of Motor Vehicles (DMV). Beginning in 2020, the DMV, in conjunction with data provided by CARB, will deny vehicle registration to non-compliant HDVs based on the model year of the HDV. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E4 | 5-20 | Provide Annual Report of Enforcement Activities: The Community Outreach and Enforcement Section of CARB’s Enforcement Division will provide an annual report to the Steering Committee to update and summarize CARB’s enforcement activities within the community. Reporting enforcement activities results is expected to help create an enforcement presence and incentive compliance. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | CARB Enforcement prepared a report for 2019 activities, but is still pending release and comments from the community members and the CSC. Enforcment staff are working on a platform to host annual reports and will be soon releasing 2020 activities report.
CARB E5 | 5-20 | Coordination with other agencies: CARB will seek opportunities to coordinate with other agencies with enforcement authority in Imperial County. Such an opportunity could consist of CARB staff working with cities to provide truck idling signage. | CARB | N/A | N/A | N/A | N/A | 553 idling inspections within community boundaries | 16 violations within boundaries | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | CARB and ICAPCD have begun discussions regarding idling reduction and coordinating enforcement efforts in the corridor. Due to COVID-19 restrictions and staff changes in ICAPCD, implementation of this strategy has been delayed.
CARB E6 | 5-20 | Enhancing CARB’s Data Management Practices: CARB is committed to enhancing the quality of enforcement data for the El Centro-Heber- Calexico Corridor. Moving forward, CARB will maintain the location of enforcement activity and received complaints to provide the Steering Committee with the most accurate data available. CARB has recently completed a visualization tool that makes CARB enforcement data more transparent and available. The tool can be accessed online by visiting https://webmaps.arb.ca.gov/edvs/. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | The EDVS tool has been updated with inspections and case information from 2019, and CARB Enforcement is actively working to update the tool to show 2020 enforcement activities.
CARB E7 | 5-20 | Providing in-person community specific training (CARB may have future online trainings available). CARB commits to deliver one training session during the first year of implementation of this plan, and expand based on attendance and input from the community. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E8 | 5-20 | CARB staff are committed to updating enforcement strategies as requested by the Steering Committee, if said strategies are enforceable by CARB staff or if CARB can reasonably accommodate the request (e.g., additional enforcement training for idling vehicles). | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E10 | 5-21 | Community outreach: Communicate specific effects of air pollution to human health and natural resources to build public support. This element of the strategy may include non-government organizations to help promote compliance by publicizing information to increase public awareness of environmental problems. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E11 | 5-21 | Citizen complaints are an important way of detecting violations that are unlikely to be detected through self-reporting or inspections. These types of complaints could potentially help detect violations and illegal acts that take place in isolated areas. CARB will promote the use of systems for reporting potential violations, referred to as “complaints.” Community will be provided with contacts and instructions to report potential violations. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E12 | 5-21 | Technology based and traditional enforcement inspection-based: CARB staff will inspect mobile and portable (i.e., PERP) air pollution sources and evaluate compliance against regulatory or permit requirements. Additionally, CARB will incorporate new technologies, where feasible, to assist and enhance enforcement work in communities. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
CARB E13 | 5-21 | CARB will present the SEP Program to the Steering Committee members to identify potential project opportunities that would benefit their community. If the project meets SEP Policy criteria, it may be listed as eligible for potential funding through the program. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | The ICAPCD submitted 3 SEP proposals for air filtration projects approved and prioritized by the CSC. One of the proposals (for Heber) was withdrawn and for the remaning ones, the District has received $ 658,515.33 for the installation of air filtration systems for schools in Calexico and El Centro.
CARB E9 | 5-21 | This strategy intends to promote voluntary compliance with applicable regulations and requirements, and to help overcome compliance barriers. Compliance will be promoted through educational programs and technical assistance. The information to communicate may include: • Education and technical assistance to the regulated community to facilitate compliance by providing information about regulatory requirements and how to meet them. • Available compliance training programs, hot lines, and publications. • Publicized success compliance stories in the area to create positive social climate and promote compliance. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | X |  |  | No updates for 2020.
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 3.CARB Guidance
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
Imperial County APCD: Calexico/El Centro/Heber
[6 empty] | Outreach |  |  | Pre-Guidance Documents |  |  |  | Guidance Development Dates |  |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Page # in Blueprint | Strategy Description in CERP | Agency | CARB Guidance Title | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Document (Text) | Draft Document Released (Date) | Final Document Released (Date) | Draft Guidance Released | Final Guidance Released | Board Hearings | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 4.CARB Incentive
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB is providing the following information on incentive programs benefiting Calexico/El Centro/Heber
Imperial County APCD: Calexico/El Centro/Heber
|  | Incentive Project Funds |  |  |  |  | Estimated Project Emissions Reductions |  |  | Outreach
|  | 2017 | 2018 | 2019 | 2020 | Cumulative Total | Oxides of Nitrogen (Tons) | Reactive Organic Gasses (tons) | PM 2.5 (tons) | Events | Attendees
Air Resources Board Programs | Carl Moyer Memorial Air Quality Standards Attainment Program | 40000 | 271600 | 91365.98 | 60000 | 462965.98 | 15.9814 | 1.7486 | 0.6635
| Clean Off Road Equipment Voucher Incentive Project |  |  |  | 600000 | 600000 | 0.37 | 0.006 | 0.004
| Clean Vehicle Rebate Project | 18000 | 18400 | 40500 | 11500 | 88400 | 0.025 | 0.0015 | 0.018
| Community Air Protection Funds |  | 31250 | 1309449 | 1002208 | 2342907 | 0.901 | 0.071 | 0.0045
| Hybrid and Zero-Emission Truck and Bus Voucher Incentive Project |  | 12000 | 12000 |  | 24000 | 0.226 | 0.01 | 0.038
| Prop 1B Goods Movement Emissions Reduction Program | 65000 |  |  |  | 65000 | 3.8214 |  | 0
| Rural School Bus Pilot Project | 330000 |  | 495000 | 495000 | 1320000 | 24.7 | 0.335 | 0.165
| Supplemental Environmental Projects |  |  |  | 658515.33 | 658515.33
| Truck Loan Assistance Program | 505906.55 | 477089 | 234813.86 | 384720 | 1602529.41
| Wildland Fire Smoke Monitoring Program |  |  | 25000 |  | 25000 | 0 | 0 | 0
| Woodsmoke Reduction |  |  |  | 5882 | 5882 | 0 | 0 | 0
Total By State Agency | Air Resources Board | 958906.55 | 810339 | 2208128.84 | 3217825.33 | 7195199.72 | 46.0248 | 2.1721 | 0.893 | 5 | 692
| Department of Community Services and Development | 106322 | 625772 | 22425 | 284150 | 1038669 | 0.7065 | 0.1135 | 0.1695
| Department of Forestry and Fire Protection | 99249 |  |  | 55470 | 154719 | 0.002 | 0 | 0
| Department of Resources Recycling and Recovery | 665028 | 1986655 | 0 | 0 | 2651683 | 1.9685 | 0.142 | 0.1975
| Department of Transportation |  |  | 922902 |  | 922902 | 0.0095 | 0.002 | 0
| Natural Resources Agency |  |  |  | 1952250 | 1952250 | 0.002 | 0.0005 | 0
| Grand Total | 1829505.55 | 3422766 | 3153455.84 | 5509695.33 | 13915422.72 | 48.7133 | 2.4301 | 1.26 | 5 | 692

## CARB Metrics Glossary
Glossary of CARB Metrics
Description of metrics that CARB will track and provide to the District, as shown on the tabs in this spreadsheet.
METRICS | DESCRIPTIONS
Outreach
Events statewide (Qty) | Number of CARB outreach/training events.
Attendees (Qty) | Number of attendees at CARB outreach/training events.
Locations of Events (Text) | List locations where outreach events are held (e.g., city names)
Enforcement and Inspections
Complaint Inspections (Qty) | Number of complaint inspections conducted by CARB.
CERP Inspections (Qty) | Number of inspections based on CERP strategies and conducted by CARB.
NOVs (Qty) | Number of notices of violation (NOVs) issued in the community by CARB.
Compliance Rate (%) | Percentage of CARB inspections that were found to be in compliance with CARB regulations.
Statewide vehicle turnover | Number of heavy duty vehicles that have permanently stopped operating in California, as a result of SB 1 implementation.
Community registration holds | Number of heavy duty vehicle registrations in the community that have been denied due to non-compliance with SB 1 provisions.
Coordination
Agencies Engaged (Qty) | Number of agencies engaged by CARB.
Names of Agencies Engaged (Text) | List names of agencies engaged by CARB.
Meetings (Qty) | Number of CARB meetings with other agencies
Resulting Actions (Qty) | Number of actions resulting from coordination with other agencies.
Description of Resulting Actions (Text) | Provide a brief description of actions resulting from coordination with other agencies.
Non-Regulatory Documents (concept papers, white-papers, etc.)
Public Documents Released (Qty) | Number of public document(s) released
Title of Non-Regulatory Document(s) (Text) | Title of non-regulatory document(s) associated with the development of statewide measures
Draft document released (Date) | Date when CARB released the draft non-regulatory document(s)
Final document released (Date) | Date when CARB released the final non-regulatory document(s)
Regulatory Process Milestones
Workshops/Webinars | Number of public workshop(s) or webinar(s) conducted providing the opportunity for stakeholders, including community members, to influence staff work prior to going to Board.
Release of 45 day or 60 day package | Start of Office of Administrative Law clock, providing the opportunity for stakeholders, including community members, to begin influencing Board member perspectives/decisions.
First Board hearing | Date when CARB's Governing Board holds initial public hearings (may be more than 1)
Potential 15 day changes | Date when CARB released "15-day changes" with revisions to draft regulatory language for public comment
Final Board hearing | Date when CARB's Governing Board approves the adoption of the regulation
OAL approval | Date when the California Office of Administrative Law approves the regulation
Community Criteria and Toxics Emissions Reductions Based on CARB’s Community-Scale Inventory
Forecasted baseline emissions (tpy) (2024) for all pollutants in planning inventory | Forecasted baseline emissions without the CARB measure
Draft emissions reductions, as available (tpy) (2024) for all regulatory pollutants in the planning inventory | Draft forecasted emissions reductions in 2024 with implementation of CARB measure, released during the regulatory development process
Final emissions reductions (tpy) (2024) for all regulatory pollutants in the planning inventory | Final forecasted emissions reductions in 2024 with implementation of CARB measure, after the regulation is adopted by CARB's Board

## 5.DISTRICT Regulatory
Annual Progress Report for AB 617 Community Emissions Reduction Programs |  |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
Imperial County APCD: El Centro-Heber-Calexico
[6 empty] | REGULATORY ACTIONS |  | 1a | 1b | 1c
Strategy Number/ ID | Page # in Plan | DISTRICT REGULATORY STRATEGIES Strategy Description | Category | DISTRICT REGULATORY METRICS Metrics to Track Progress, as Identified in Imperial Plan | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
R-1 | 4-5, 6-1 | Identification of potential control options on two industrial sources which are subject to expedited BARCT schedule, but are outside of the Corridor. | Regulatory/ Permitting | 1. A description of the outcome of the District’s control measure cost-effectiveness analysis. 2. A description of any proposed changes to Rule 400.2 or 400.4 resulting from the District’s review, along with a schedule for those proposed changes. | 1. The District evaluated cost effectiveness for retrofitting Spreckles Sugar's boilers to meet the new BARCT emissions limit of 7 ppmv limit in Rule 400.2. Due to seasonal operation of Spreckels, the cost for retrofitting the boilers is higher than the recommended cost effectiveness threshold. As such, Spreckels will not be required to be meet the 7 ppmv threshold. U.S. Gypsum is also required to comply with AB 617 BARCT reqs. USG is the only source that operates Wallboard Kilns, and therefore subject to Rule 400.4. The District proposed a BARCT NOx limit for wallboard kilns of 7 ppmvd @ 3% oxygen. Upon further District analysis, no available options were cost-effective that would achieve the proposed limit. The District confirmed that the most effective technology (Ultra-Low-NOx burners) is already in place at USG, thereby meeting BARCT (see attached Cost-Effectiveness). 2. District amended Rule 400.2 to establish new BARCT limits for emissions units installed or modified after January 1, 2020 (see attached Rule 400.2). | Draft Rule 400.2 was released for public review on October 23, 2019. | Revised Rule 400.2 was formally adopted on November 26, 2019. | Yes, action/approval from the Air District Board, which occurred on 11/26/19. | a) The District carried out the analysis and outreach to satisfy the expedited schedule for the implementation of BARCT. Two facilities in Imperial County, but outside the Corridor, were subject to expedited implementation of BARCT - Spreckels Sugar that operates large industrial boilers, and U.S. Gypusm that operates wallboard kilns. Upon reviewing available emissions control options and their cost-effectiveness, the District concluded that any additional retrofitting was not cost-effective, and therefore, both sources were in compliance with BARCT requirements and amended District Rule 400.2 and existing District Rule 400.4. b) N/A c) N/A | Not applicable.
R-2 | 4-5, 6-5 | CARB proposed statewide measures that would result in emission reductions within the Corridor. These measures include: Advanced Clean Cars 2, Advanced Clean Truck, Heavy-Duty Inspection and Maintenance, Heavy Duty "Omnibus" Low NOx Engine Standard and Small Off-Road Engine Amendment; Zero-Emission Vehicle Fleet Rule. | Regulatory/ Permitting | [SEE CARB REGULATORY METRICS TAB]
A-1 | 4-8, 6-1 | District will utilize CARB's Technology Clearinghouse as a reference in developing BACT and T-BACT for any new or modified source permitting processes within or directly surrounding the Corridor. | Regulatory/ Permitting | 1. The date the District began using the Technology Clearinghouse as a reference in developing BACT and T-BACT determinations for sources within or directly surrounding the Corridor. 2. The number and type of permit applications that underwent a BACT or T-BACT determination where the Technology Clearinghouse was used as a reference. | 1. The District began utilizing preliminary tools offered under CARB's Technology Clearinghouse in October 2019. 2. Since the Technology Clearinghouse is still under development, with the BACT and TBACT components still being developed by CARB, the BACT and T-BACT determinations by the District have been limited. However, the District analyzed six (6) new permit applications in the past year for sources within or directly adjacent to the Corridor for BACT and T-BACT compliance with District Rules and Regulations. The source types were: 1 emergency generators, 1 portable combustion unit, 3 paint booth operations, and 1 soil remediation. | N/A | N/A | N/A | a) Strategy is being implemented, and will continue expanding as additional sections are added to the CARB Technology Clearinghouse, including the BACT and TBACT components. b) Given the general approach of this strategy, and that the Clearinhouse is still in development by the State, an estimated of potential emissions reductions are presently not available. However, through this strategy, older control technologies for sources inside and surrounding the Corridor will be replaced with newer, greater efficiency ones, that will further reduce air emissions that would otherwise impact the Corridor and Imperial County. | N/A
M-5 | 4-17, 6-4 | District has updated their Policy #34 "Agricultural Burning Procedures for Allocating Acreage, Burn Day Decisions and Tracking". | Regulatory/ Permitting | Number of acres burned per day under Policy #34 (including quantification of the number of acres characterized as “Special Burns”) and an estimate of emissions. | The maximum daily burns recorded on any given day between 1/1/2021 and 9/28/2021 has been 650 acres, which is well below the 1,600 acres per day limit. Total estimated Max PM2.5 emissions based on 650 acres burned is 11.21 tons which is 15.5 tons less than estimated maximum daily emissions.The implementation of the new policy which increased the number of agricultural fields defined as "Special", has ensured that field burn smoke impacts are minimized to the greatest extent. | 2/13/2019; 3/14/2019; and 6/19/2019 | Approved and implementation began on 11/14/2019. | No action required | (a)The policy is being implemented by ICAPCD Enforcement Staff when designating ag burn locations. (b) Between 1/1/2021 and 9/28/2021 Maximum daily acreage burned on a single day totaled 650 acres, this is well below the policy's daily limit of 1,600 acres per day and about 40% of maximum daily emissions. (c) This does not apply. The Air District designates and authorizes burn permits. | Not applicable.

## 6.DISTRICT Enforcement
Annual Progress Report for AB 617 Community Emissions Reduction Programs |  |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
Imperial County APCD: El Centro-Heber-Calexico
[6 empty] | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | 1a | 1b | 1c
Strategy Number/ ID | Page # in CERP | DISTRICT ENFORCEMENT STRATEGIES Strategy Description | Category | DISTRICT ENFORCEMENT METRICS Metrics to Track Progress, as Identified in Imperial CERP | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
E-1 | 5-15, 6-1 | District is in the process of installing cameras in the desert, outside of the Corridor, and will make this video available to the public so as to monitor for potential exposure concerns of fugitive dust. | Enforcement | 1. The date cameras were installed in the desert west of the Corridor. 2. The date the video feeds from these cameras were publicly available. 3. The reason(s) for any significant periods of downtime (i.e., >1 week) in the video feed. 4. A description of any exposure events identified as originating from the desert west of the Corridor and any resulting enforcement activity. | District is working with University of California, San Diego (UCSD) to host the camera feeds through their online camera video network. Implementation was delayed due to issues surrounding COVID-19 pandemic. District is expected to having cameras installed and operating by late 2022. The visual platform, the strategic installation and operation of high definition cameras around and within Imperial County (IC) have recently resumed. The two sites are Superstition Mountain (approx. 16 miles northwest of El Centro) and the other is yet to be determined, conceptually east of IC above the Algodones Dunes. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | To be determined. | Not applicable. | a) Implementation was delayed due to the COVID-19 pandemic and the wildfires in Southern California, which both impacted the District's coordination with UCSD on the project. b) District is expected to having cameras installed and operating by late 2022. c) Not applicable.
E-2 | 5-16, 6-2 | District to perform cross agency training of their rules to help with the identification of specific types of violations. | Enforcement | For each cross-agency training session provide: 1. The date, topic, and number of attendees. 2. A summary of any action items, concerns, or solutions discussed. | Presentations on Agricultural Burning and Residential Burning are being developed and scheduled to be presented to County Fire Dept. and Sheriffs Dept. The Cities Fire and Police Department will also be invited. Presentations on Fugitive Dust Rules are being developed and will be provided to County Building Department and Cities Building Department. Proposed trainings were scheduled for October 2020, which occurred remotely through Zoom. | Agricultural Burning, Residential Burning, Fugitive Dust Rules | One for burning activities. One for Fugitive Dust Rules. | Trainings will be held via Zoom due to pandemic. | N/A | N/A | N/A | N/A | N/A | Not applicable | (a)Draft presentations were developed. Content was reviewed internally. (b)Emissions and exposure reductions benefits will be expected as there will be several agencies and staff fully aware of rules and what will be consider a potential violation. (c) There are no relevant land use or permitting issues for this strategy. | (a) Implementation took place in October 2020. (b) As indicated the presentations were developed and presented to agencies in October 2020.(c) Not applicable.
E-3 | 5-16, 6-2 | District is proposing to provide annual training to industry, with certain focused training available upon request. Along with enforcement related workshops geared for the community. | Enforcement | For each industry training session and public workshop provide: 1. The date, topic, and number of attendees. 2. A summary of any action items, concern, or solutions discussed. 3. A description of the outreach conducted. | Presentations on Agricultural Burning will be provided to the farming community thru collaboration with the Imperial County Farm Bureau. In addition, two presentations of our Fugitive Dust Rules have already been provided to Imperial Irrigation District staff on 12-12-2019 and 1-23-2020. The Air District will also provide this presentation to local construction companies such as Granite Construction, Pyramid Construction, API, and others. The proposed presentations were provided on October 2020. | Agricultural Burning, targeting the Farming Industry and Fugitive Dust Rules, targeting the Construction Industry. | One for burning activities. One for Fugitive Dust Rules to Construction Industry. Two presentations have been provided to IID since the adoption of the CERP. | Trainings will be held via Zoom due to pandemic. Two in-person presentations have been provided to IID. | N/A | N/A | N/A | N/A | N/A | Not applicable | (a)Draft presentations were developed. Content was reviewed internally. (b)Emissions and exposure reductions benefits will be expected as industry will receive valuable training on applicable rules. (c) There are no relevant land use or permitting issues for this strategy. | (a) The ICAPCD has provided two presentations on the Air Districts Fugitive Dust Rules to Imperial Irrigation District. Additional presentations have been delayed due to pandemic impacts on staff schedules, work assignments and related duties.(b) As indicated, the presentations are being developed and presentations to agencies will be provided in October 2020. (c) Not applicable.
E-4 | 5-16, 6-2 | District is proposing to increase community outreach through the publication of a quarterly newsletter to include information on enforcement statistics and rule changes. | Enforcement | The publication date for each quarterly newsletter and a summary of any enforcement- or rule-related discussion topics. | District published first newsletter (ICAPCD Bulletin, Vol. 1) on April 3, 2019, which included an overview of the AB 617 Program and the El Centro-Heber-Calexico Corridor. This newsletter also provided information on District's revisions to ICAPCD Policy No. 34, Agricultural Burning. Second quarterly newsletter (ICAPCD Bulletin, Vol. II was published on June 27, 2019, and included information on District's AB 617 Website, Enforcement Training, and new District Staff. On January 16, 2020, District published a Press Release documenting the approval of the CERP by the California Air Resources Board on Jan. 15, 2020 in El Centro, CA. District released a news video on January 22, 2020 with interviews of CARB officials, local County Board of Supervisors, and Assemblyman Eduardo Garcia discussing the achievement of CERP being approved by CARB. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No action required. | (a) Due to severity of COVID-19 pandemic in Imperial County, some District Staff were reassigned to respond to the crisis. Since conditions have recently improved, District is resuming normal operations, and plan to resume newsletters publication in early 2022. (b) & (c) not applicable. | Not applicable.
E-5 | 5-16, 6-2 | District and CARB are proposing to form a dedicated enforcement outreach team made up of staff from the agencies to actively engage with the CSC and respond to community concerns. | Enforcement | 1. The date the outreach team was assembled and the current list of members. 2. The number of presentations or meetings with the Steering Committee. 3. A description of community concerns and associated responses/solutions. | District and CARB Staff have regularly engaged with the CSC at their regularly scheduled meetings in 2020 and 2021, and presented a comprehensive update on recent Enrocement Actions/Data at the Oct. 14, 2020 CSC meeting. The AB 617 CSC want to formally establish a Technical Advisory Committee and are looking into the Brown Act. | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | No action required. | Not applicable. | Formation of the Technical Advisory Committee was delayed due to impacts on District Staff and Resources because of the COVID-19 pandemic. District will look into how the Committee can be established.
E-6 | 5-17, 6-2 | District to facilitate the complaint process in order to increase public access to filing complaints and more accurately capture complaint information. | Enforcement | 1. The date website changes are implemented. 2. The date an online complaint form is created. 3. The number of complaints received through the online compliant form. | On August 31, 2020 the ICAPCD made the required website improvements. It has added a feature to allow the public to file a complaint online. It has also published the complaint line number as well as a direct link to the complaint page. | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | No action required. | (a) The website changes took effect on August 31, 2020. (b) the online complaint form was also created and made publically accessible on August 31, 2020. As of September 29, 2021 there have been some complaints recevied through the online complaint form. | Not applicable.
E-7 | 5-17, 6-2 | District is proposing to revise internal Policy #17 "Guidelines for Staff Processing and Investigation of Complaints". | Enforcement | The date an updated Policy #17 is adopted and a summary of the revisions made. | Over the last couple of months the Air District evaluated and compared the Air District's Policy 17 - Guidelines for Staff Prcessing and Investigating Complaints with those of other Air Districts including, SJVAPCD, Ventura County APCD, Santa Barbara APCD and Bay Area AQMD. The ICAPCD has drafted a revised policy based on the best methods that can be implemented locally. | An update on the policy will be provided to AB617 committee. | One update will be provided. | Via Zoom meeting | N/A | N/A | N/A | N/A | N/A | No action required. | N/A | This revised District policy was submitted to CARB to be reviewed on June 2021.
E-8 | 5-17, 6-2 | District is proposing to revise internal Policy #18 "Notices of Violation Issuance and Follow Up" and Policy #28 "Notices to Comply - Administrative Guidelines". | Enforcement | 1. The date an updated Policy #18 is adopted and a summary of the revisions made. 2. The date an updated Policy #28 is adopted and a summary of the revisions made. | Policies 18 and 28 were reviewed and evaluated based on comparison with other Air Districts similar policies. | An update on the policy will be provided to AB617 committee. | One update will be provided. | Via Zoom meeting | N/A | N/A | N/A | N/A | N/A | No action required. | (a) Revised policies have not yet been implemented. (b) Uniform investigation steps and procedures will be followed by Enforcement staff. (c) Does not apply. | This revised District policy was submitted to CARB to be reviewed on June 2021.
E-9 | 5-18, 6-2 | District is proposing to perform an annual retrospective review of enforcement statistics in order to identify areas of improvements. | Enforcement | 1. The date the annual review of compliance and enforcement is released to the public. As part of this review, the District will track and report on: 2. The number of inspections conducted, including type, date, and location. 3. The number of NOVs and NTCs issued, including the date and regulation cited. 4. The number of complaints received, including type and resolution. 5. The number of NOVs and NTCs resolved. 6. The non-compliance rate for the year. | 1. The annual review of compliance and enforcement will be provided to the public on October 1, 2021. 2. The attached ICAPCD Compliance & Enforcement Report (Enforcement Report) is based on permitted source inspections in the Corridor conducted in 2020. There was a total of 253 inspections conducted out of a maximum of 264 (for details, see attached Enforcement Report). 3. See attached Enforcement Report to review data on the NOVs and NTCs that were issued in 2020 in the Corridor. 4. See attached Enforcement Report which shows complaint date, complaint number, complaint type, location & description of complaint and the action taken during investigation. 5. See attached Enforcement Report for number of NOVs and NTCs resolved. 6. See attached Enforcement Report for non-compliance rate for 2020 for permitted sources in the Corridor. | N/A | N/A | N/A | 253 | 24 | 30 | 23 | 9 | No action required. | Strategy is already being implented. See data provided in these tabs and attached ICAPCD Compliance and Enforcement Report for 2020. | Not applicable.
E-10 | 5-18, 6-5, 6-6 | District is proposing to work in conjunction with CARB to identify enforcement strategies within CARB's current regulatory programs that could benefit the Corridor. | Enforcement | [SEE CARB ENFORCEMENT METRICS TAB for all details on this joint District-CARB Strategy]. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CARB ED strategies found in the Enforcement Plans in each CERP should not require action by either the CARB Board or the Air District board. | Not applicable. | Full implementation for El Centro-Heber-Calexico CERP began January 15, 2020. There currently, are no strategies behind the proposed due date in the Enforcement plan.

## 7.DISTRICT Coordination
Annual Progress Report for AB 617 Community Emissions Reduction Programs |  |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
Imperial County APCD: El Centro-Heber-Calexico
[6 empty] | COORDINATION |  | OUTREACH / EDUCATION EVENTS |  |  | 1a | 1b | 1c
Strategy Number/ ID | Page # in CERP | DISTRICT COORDINATION STRATEGIES Strategy Description | Category | DISTRICT COORDINATION METRICS Metrics to Track Progress, as Identified in Imperial CERP | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | Topic of Outreach Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
L-2 | 4-13, 6-3 | District to track and review local general plan updates on a quarterly basis and issue comment letter when local action has the potential to affect air quality or exposure in the Corridor. | Coordination | 1. The number of general plan updates considered and commented on by the Steering Committee. 2. A description of any responses/actions by local agencies (in response to the comment letter(s) received). | This strategy is currently in development. | 2 | Imperial County Planning & Development Services; City of El Centro, | N/A | 0 | N/A | To be determined. | The District has held meetings with the Imperial County Planning & Development Services to determine the agency's upcoming schedule of reviewing/updated Land Use Policies in the Corridor, and the Housing Element of the General Plan is scheduled for and update in 2021/2022. The District also held a meeting with the City of El Centro, which is in the process of developing a new Environmental Justice (EJ) Element to their General Plan. District will work with City of El Centro to make available the Draft EJ Element to the CSC for their review, and to give a presentation in an upcoming CSC meeting. | This strategy is a Tier II project; thus implementation has not been delayed. The District and CSC will continue coordinating with entities such as the City of El Centro, City of Calexico, and Imperial County to track and review local general plan updates as they become available, and to issue a joint comment letter, when a local action has the potential to affect air quality or exposure in the Corridor.
L-3 | 4-13, 6-3 | Creation of an area wide plan that identifies potential locations where urban greening projects could be implemented to mitigate air quality impacts to sensitive receptors. This would inform the projects sought under strategy M-2. | Coordination | [SEE STRATEGY I-2 FOR METRICS] | N/A | N/A | N/A | N/A | N/A | N/A
L-4 | 4-14, 6-4 | District to assess the feasibility of implementing emission reduction measures in the open areas and/or desert areas west of the Corridor. | Coordination | 1. The number and date of meetings held with stakeholders to discuss the feasibility of implementing measures that reduce emissions in the open areas/desert areas west of the Corridor. 2. A description of the measures considered, along with a discussion of feasibility, proposed next steps, and metrics to track in the coming year. | This strategy is currently in development. | 0 | N/A | N/A | 0 | N/A | To be determined. | Conversations in progress to bring stakeholders to the table. | This strategy is a Tier II project; thus implementation has not been delayed. The District will coordinate with local agencies and stakeholders to schedule a meeting by 2022 to discuss the feasibility of measures for this strategy.
T-1 | 4-14, 6-4 | District to assess the feasibility of implementing measures that reduce the impact of activities at the border, such as the evaluation of alternative routes for traffic coming through the ports-of-entry. | Coordination | 1. The number and date of meetings held with local transportation agencies and other bodies to discuss the feasibility of implementing measures that reduce the impact of activities at the border. 2. A description of the measures considered, along with a discussion of feasibility, proposed next steps, and metrics to track in the coming year. | This strategy is currently in development. | 2 | SCAG and Air Quality Task Force (AQTF) | Border feasibility Projects | 2 | SCAG: Zoom Call AQTF: Mexicali, Baja California | No Action needed by CARB at this time. | Conversations in progress to bring stakeholders to the table. | This strategy is a Tier II project; thus implementation has not been delayed. The District will coordinate with local transportation agencies to schedule a meeting by 2022 to discuss the feasibility of measures for this strategy.
T-2 | 4-14, 6-4 | District to solicit input from local school districts, senior facilities and medical centers to determine if installing signage that encourages vehicles not to idle near these sensitive receptor land uses would be found beneficial. | Coordination | 1. The date and number of attendees for each public workshop held related to signage initiatives for reducing idling. 2. A description of the measures considered, along with a discussion of feasibility, proposed next steps, and metrics to track in the coming year. | This strategy is currently in development. | 0 | N/A | N/A | 0 | N/A | To be determined. | Conversation in progress to bring stakeholders to the table. | This strategy is a Tier II project; thus implementation has not been delayed. The District will reach out to these affected groups/sensitive receptors to schedule a workshop by 2022 to gather input and determine feasibility.
T-3 | 4-15, 6-4 | District to partner with CARB to conduct education and outreach to reduce the amount of truck idling in the Corridor. | Coordination | For each public workshop held for local businesses with heavy-duty truck fleets operating in the Corridor: 1. The date, topic, and number of attendees. 2. A description of the outreach conducted. | This strategy is currently in development. | 0 | N/A | N/A | 0 | N/A | To be determined. | Conversations in progress to bring stakeholders to the table. | Coordination efforts between District and CARB were delayed due to the COVID-19 pandemic, but with local situation improving, the public workshop will be held remotely with CARB by 2022 for local heavy-duty truck fleets to provide education to reduce idling.
M-1 | 4-15, 6-4 | District is proposing to install air filtration systems on up to 240,000 square feet of building space at sensitive receptor locations including, but not limited to, schools and senior centers. | Coordination | A description of each air filtration system installed in the Corridor, including the location, technology deployed, number of square feet conditioned, and number of sensitive receptors affected. | Air Filtrations systems have been installed at the following amount of schools: 2 out of 2 schools in Heber, 3 out of 11 schools in Calexico, and 7 out of 16 schools in El Centro as of September 2021. | Minimum of once per month with IQ Air North America, Inc. (12 total). | IQAir North America, Inc (IQAir).; El Centro Elementary School District | Improving Indoor Air Quality through enhanced air filtration at Schools in the Corridor. | District provided updates to the CSC 4 times in 2020 at monthly meetings. District held 1 workshop with School Districts in the Corridor. | Calexico Neighborhood House (Calexico, CA); Remote Meetings with CSC & public and School District Workshop via Zoom. | District Board approved Agreements for Dogwood & Heber Schools on June 23, 2020. District Board approved Agreement for De Anza School on August 11, 2020. | a) District has worked closely with IQAir to schedule site assessments and installation of air filtrations systems at Schools in the Corridor, based on the input from the CSC which was documented in Imperial's CERP. b) The enhanced air filtration systems reduce the exposure of air emissions to students and faculty by filtering up to 95% of all airborne particles, including PM2.5, down to 0.003 microns in size, including dust, mold, allergens, and harmful tailpipe emissions. c) Not applicable. | N/A

## 8.DISTRICT Incentive
Annual Progress Report for AB 617 Community Emissions Reduction Programs |  |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
Imperial County APCD: El Centro-Heber-Calexico
[6 empty] | INCENTIVE PROJECTS METRICS |  |  | OUTREACH EVENTS METRICS |  |  | 1a | 1b | 1c
Strategy Number/ ID | Page # in CERP | DISTRICT INCENTIVE STRATEGIES Strategy Description | Category | DISTRICT INCENTIVE METRICS Metrics to Track Progress, as Identified in Imperial CERP | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Topic of Outreach Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
I-1 | 4-10, 6-3 | District to participate in the Woodsmoke Reduction Program administered by CARB. Identification of three projects for replacement of residential wood burning devise with more efficient equipment. | Incentives | 1. The number and type of wood burning devices replaced under the Woodsmoke Reduction Program, along with the replacement technology, and associated emission reductions. 2. The amount of incentive funds received under the Woodsmoke Reduction Program. | We Currently have nine (9) signed agreements with two additional agreements pending. A meeting via telephone was conducted in October between vendors and staff with a second meeting with residents to answer all questions. | 62605 | 38 Fireplace retrofits | PM2.5 estimated less than 1 t/y, or 0.0027 t/d | October 2019: Conducted Surveys; June 2020: Sent Letters to participants | 2 | Due to Covid Events were conducted via telephone conference. | N/A | N/A | Due to COVID-19, we are not able to access homes for pre-inspections. All conversations were done through telephone calls to each interested party. In addition, vendor(s) felt the heat was a major factor, as home inspections would require rooftop inspections as well. Temperatures are expected to cool by October. Expect to install cleaner burning equipment by Winter 2022.
I-2 | 4-11, 6-3 | District will monitor for and identify potential grant programs for urban greening projects. Any funding obtained would be put towards projects sought under strategy M-2. | Incentives | 1. A description of any newly identified urban greening incentive programs applicable to the Corridor. 2. The number of applications submitted by the District or partner agencies and accepted. 3. The amount of incentive funds received from urban greening incentive programs. 4. The number and date of meetings held with local representatives from the planning departments and communities of El Centro, Heber, and Calexico to discuss potential locations for urban greening projects. 5. The number and type of urban greening projects implemented, along with a description of any nearby sources or sensitive receptors. 6. The amount of incentive funds and/or AB 617 funds used towards urban greening projects. | 1. This strategy is currently in development, as it is a Tier 2 Strategy. District has been monitoring potential grant programs for urban greening projects through local, State, and federal agencies. 2. No applications have yet to be filed. 3. No additional funds received to date. 4. District met with City of Calexico on 02/19/20 and met with City of El Centro on 03/10/20 to discuss this strategy. 5. District is working with CSC to develop a Project Plan associated with this Tier 2 Strategy and the Tier 1 Mitigation Strategy below (M-2). 6. In Progress, and will begin implementation once the Project Plan for this strategy is approved by CARB. |  |  |  | Discussion with CSC and public regarding budget for Urban Greening Projects; Presentation by the City of Calexico on potential urban greening projects to benefit residents; Project Plan Presentation and discussion with CSC on development of criteria for this Mitigation Strategy on 09/09/20. | 3 | Calexico Neighborhood House (Calexico, CA); Remote Meetings with CSC & public and School District Workshop via Zoom. | The Project Plan for M-2 requires approval by CARB before implementation can commence. | N/A | (a) Strategy I-2 is classified as a Tier 2 Strategy, and is thus in continued development. (b) Strategy M-2 will be implemented once the Project Plan, which sets the project application & implementation criteria for proposals received, is approved by CARB. The Project Plan is currently in development with advisement from the CSC, with the goal of submitting the Plan to CARB for approval prior to the end of 2020 calendar year. (c) Emissions reduction targets are projected to be fully met within the five-year timeframe, once implementation commences upon approval of Project Plan for M-2.
L-1 | 4-12, 6-3 | District to identify locations that could benefit from paving projects to mitigate fugitive windblown dust and unpaved road dust. This would inform the projects sought under strategy M-3. | Incentives | 1. The number and date of meetings held with local public works departments and other representatives from the communities of El Centro, Heber, and Calexico to discuss potential locations for paving projects. 2. The number and location of paving projects implemented, along with an estimate of the total acres paved, associated emission reductions, and a description of any nearby sensitive receptors. 3. The amount of incentive funds and/or AB 617 funds used towards paving projects. | 1. District met with City of Calexico Public Works on 02/19/20, City of El Centro Public Works on 03/10/20, and with El Centro City Manager & Staff on 09/24/20 to discuss potential locations for this strategy. District also met with Calexico City Manager on 09/09/20 to discuss proposed Calexico Alleyways Paving Project. 2. Parking lot paving project was completed at Maintenance & Operations Department at Calexico High School (Calexico, CA), as an early action emissions reduction project, approximately 39,000 sq. ft. in size. 3. $203,240. | 203240 | 1 paving project. | PM10 Emissions- 2.26 tons/year | CSC meeting in July 2019 to approve Calexico High School parking lot paving project as early emissions reduction project; Potential locations of paving projects in the Corridor with City of Calexico and City of El Centro; District held online workshop with School Districts in the Corridor on 08/04/20 to discuss potential paving projects at their schools in the Corridor; Project Plan Presentation and discussion with CSC on development of criteria for this Mitigation Strategy on 09/09/20. | 7 | ECRMC Community Education Center (El Centro, CA); ICAPCD Office (El Centro, CA); Calexico City Hall (Calexico, CA); Remote through Zoom with City Officials and School Districts. | Strategy requires approval from District Board; Project Plan for M-3 requires approval by CARB before implementation can commence. | In progress; District will continue working with Staff and officials from local cities and the County to identify potential locations for paving projects. Full implementation will commence once the Project Plan has been approved by CARB, and an RFP is published by the District for the submittal of formal project proposals. | (a) (b) Strategy M-3 will be implemented once the Project Plan, which sets the project application & implementation criteria for proposals received, is approved by CARB. The Project Plan is currently in development with advisement from the CSC, with the goal of submitting the Plan to CARB for approval prior to the end of 2020 calendar year. (c) Emissions reduction targets are projected to be fully met within the five-year timeframe, once implementation commences upon approval of Project Plan for M-3.
M-2 | 4-16, 6-3 | District is proposing to initially designate a minimum of $200,000 in funding towards the implementation of urban greening projects within the Corridor. | Incentives | [SEE STRATEGY I-2 FOR METRICS] | District is working with CSC to develop the Project Plan to establish the project criteria for this mitigation strategy. June 2020 – City of Calexico gave a presentation to the CSC on potential urban greening project locations. The Project Plan has been approved by CARB and and was developed on January 2021 and later revised on February 2021. 7 project proposals have been submitted and approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors. • June 2020 – City of Calexico gave a presentation to the CSC on potential urban greening project locations. • The Project Plan has been approved by CARB and and was developed on January 2021 and later revised on February 2021. • 7 project proposals have been submitted and approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors. • District is working with CSC to develop the Project Plan to establish the project criteria for this mitigation strategy. • June 2020 – City of Calexico gave a presentation to the CSC on potential urban greening project locations. • The Project Plan has been approved by CARB and and was developed on January 2021 and later revised on February 2021. • 7 project proposals have been submitted and approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors. |  |  |  | See I-2 | See I-2 | See I-2 | See I-2 | 7 project proposals have been submitted and approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors.
M-3 | 4-16, 6-3 | District is proposing to fund parking lot paving projects within the Corridor, as funding permits. | Incentives | [SEE STRATEGY L-1 FOR METRICS] | District is working with CSC to develop the Project Plan to establish the project criteria for this mitigation strategy. The Project Plan has been approved by CARB and and was developed on January 2021 and later revised on February 2021. 7 project proposals have been submitted and 6 were approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors. |  |  |  | See L-1 | See L-1 | See L-1 | See L-1 | 7 project proposals have been submitted and 6 were approved by the CSC members on the September 2021 meeting, project proposals are yet to be reviewed by CARB and our Board of Supervisors.
M-4 | 4-17, 6-4 | District is proposing to assist as many schools as funding permits in the Corridor in implementing the School Flag Program. | Incentives | 1. A list of schools in the Corridor implementing the school flag program, including identification of any schools that are new to the program. 2. A description of any enhancements made to the school flag program. 3. The amount of incentive funds and/or AB 617 funds used towards paving projects. | 1. District is working with CCV and the CSC to develop a Project Plan for this mitigation strategy. 2. In Progress; implementation will being once the Project Plan is drafted and submitted to CARB for approval. 3. In conversation with Schools to figure out a way to implement digital colored marquee without interfering the School’s already set up programming |  |  |  | District held online workshop with School Districts on 08/04/20 to discuss existing and expansion/improved Flag Program at their schools in the Corridor. | 1 | Remote meeting through Zoom. | To be determined. | Not applicable. | (a)(b) Strategy M-4 will be implemented once the Project Plan, which sets the project application & implementation criteria for proposals received, is approved by CARB. The Project Plan is currently in development with advisement from the CSC, with the goal of submitting the Plan to CARB for approval prior to the end of 2020 calendar year. (c) Objectives and metrics are projected to be fulfilled, to get as many schools implementing the enhanced flag program during the five-year timeframe.
M-6 | 4-18, 6-5 | District is proposing to replace 5 school buses with electric school buses between 2020 and 2025. | Incentives | 1. The number of school buses replaced, along with the replacement technology (i.e., electric or compressed natural gas [CNG]), and associated emission reductions. 2. The amount of incentive funds and/or AB 617 funds used towards school bus replacement projects. | ICAPCD has completed one school bus replacement project (replace old diesel bus with electric bus) in 2020 at Calexico Unified School District (CUSD). | 314449 | 1 school bus replacement project; 1 charging station (infrastructure) project for CUSD. | NOx - 0.09 tons/yr ROG - 0.01 tons/yr PM10 - 0.01 tons/yr | District held online workshop with School Districts in the Corridor on 08/04/20 to discuss availability of AB 617 funding for school bus replacement projects at their schools. | 1 | Remote meeting through Zoom. | Individual projects through this strategy will be approved by District Board. | (a) Strategy is underway and will be further implemented once proposals are submitted per the RFP that the District will release in Fall of 2020. (b) Emissions reductions for pollutants such as Nox, PM10, and PM2.5 will benefit the residents and various sensitive receptors in the community. (c) Not applicable. | (a)(b) Implementation is currently underway for M-6, with District releasing an RFP for school bus replacement projects in Fall of 2020. (c) Emissions reduction targets are projected to be fully met within the five-year timeframe, once implementation commences upon approval of Project Plan for M-6.