## README
Annual Progress Report for AB 617 Community Emissions Reduction Programs
DRAFT Data Collection Template - Stockton Community
Purpose: Use this Excel spreadsheet template to provide status updates for each strategy, as identified in your community emissions reduction program. Attach this spreadsheet to the Microsoft Word template that describes overall progress for your program. This spreadsheet includes the following tabs:
CARB Metrics: This workbook summarizes the metrics CARB will use to track progress of statewide strategies in the "Community Emissions Reduction Program Stockton" (Plan). The CARB strategies included in the Plan are grouped into three categories with a separate tab for each: Regulatory, Enforcement, and Guidance. The CARB Incentives tab provides metrics for incentive projects that are located in the Stockton community and are funded by a statewide incentive program.
1. CARB Regulatory Metrics: | CARB regulatory metrics track CARB's regulatory development process for strategies identified in the Plan. These metrics are cumulative since the initiation of regulatory development.
2. CARB Enforcement Metrics: | CARB enforcement metrics are cumulative since 2019.
3. CARB Guidance Metrics: | CARB guidance metrics track CARB's guidance development process and are cumulative since the initiation of guidance development.
4. CARB Incentive Metrics: | CARB incentive metrics are cumulative since 2017.
DISTRICT Metrics: This workbook also summarizes the metrics that the San Joaquin Valley Air Pollution Control District (SJVAPCD) will use to track progress of district strategies included in the "Community Emissions Reduction Program Stockton" (Plan).
5b to 5h. DISTRICT Metrics: | DISTRICT metrics track the progress of all strategies that are not included on the CARB tabs, as listed in Chapter 7 in the Plan.
CARB Emissions Benefit Caveats: • CARB adopted the Ocean-Going Vessels At Berth Amendment on August 27, 2020. Benefits for this regulation are shown here as the community emission inventory (May-June 2020) did not inlcude the benefits of this regualtion in future years 2024/25 and 2029/30. • CARB adopted the Advanced Clean Truck on June 25, 2020. Benefits for this regulation are shown here as the year-1 community emission inventories did not inlcude this regulation in the baseline projections for 2024/25 and 2029/30. • CARB adopted the Heavy-Duty Engine and Vehicle Omnibus regulation (previosuly HD Low-NOx Engine Standard) on August 27, 2020. Benefits for this regulation are shown here as the community emission inventories (May-June 2020) did not inlcude this regulation in the baseline projections for 2024/25 and 2029/30. • TRU Regulation was not included in the benefits calculation last year. Preliminary reg inventory data was not available until mid 2021. We might want to loop back with TTD on the estimated benefits.
REFERENCES
CARB Community Air Protection Blueprint, October 2018, Appendix C, pages C-38 to C-40
https://ww2.arb.ca.gov/our-work/programs/community-air-protection-program/community-air-protection-blueprint
Community Emissions Reduction Program Stockton
http://community.valleyair.org/selected-communities/stockton/
CARB document <<STAFF REPORT NAME>> released <<MONTH>> <<DAY>>, <<YEAR>>, available at:
<<URL LINK OF STAFF REPORT>>
<<DISTRICT BOARD RESOLUTION NAME>>
<<DISTRICT BOARD RESOLUTION URL LINK>>
CARB Board Resolution -TBD
QUESTIONS? Send an email to: | CommunityAir@arb.ca.gov
Date last modified: | Version | CARB Authors
2021-07-02 | 1.0 | Jeremy Herbert; Hanjiro Ambrose
Policy metrics vintage - June 16, 2021
Incentive metrics vintage - TBD
Enforcement metrics vintage - TBD
Guidance metrics vintage - June 16, 2021
CARB-Air District Discussion Only ¦ Draft Deliberative

## 1.CARB Regulatory
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
San Joaquin Valley APCD: Stockton
|  |  |  | Outreach |  |  | Non-Regulatory Documents |  |  |  | Regulatory Process Milestones | [5 empty] | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable) |  | Community Criteria and Toxics Emissions Forecasted Baseline Emissions (tpy) (2025) | [8 empty] | Community Criteria and Toxics Emissions Draft Emissions Reductions, As Available (tpy) (2025) | [8 empty] | Community Criteria and Toxics Emissions Final Emissions Reductions (tpy) (2025)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | CARB Regulation | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Non-Regulatory Document(s) (Text) | Draft Document Release(s) (Date) | Final Document Release(s) (Date) | Workshops/Webinars | Release of 45 day or 60 day package | First Board hearing | Potential 15 day changes | Final Board hearing | OAL approval | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM | NOx | ROG | PM 10 | PM 2.5 | CO | NH3 | SOx | TOG | DPM
Commercial Harbor Craft Regulation Amendments | 128 | CARB’s existing commercial harbor craft regulation was adopted in 2007 and will be fully implemented by the end of 2022. CARB is working through a public process to consider additional amendments that may further reduce emissions and pursue more stringent in-use standards, with consideration for Tier 4 engine technology and near-zero and zero emission technologies. | Commercial Harbor Craft Regulation | 7 | 892 | 101 Pacific Avenue Long Beach, California 90822 1001 I Street Sacramento, CA 95814 Webcast Webinar Zoom Teams | 5 | 1. Revised Draft Regulatory Language 2. Draft Regulatory Language 3. Draft Cost Metrics 4. Funding Programs for CHC 5. Proposed Concepts for Commercial Harbor Craft in California | 1. 3/16/2021 2. 9/30/2020 3. 9/30/2020 4. 9/30/2020 5. 2/27/2020 |  | 7 | [6 empty] | This strategy requires CARB action during at least one board hearing. | a) Public workshops (42); Public workgroup meetings (1); Presentation stakeholder or trade association meetings (4); Release of detailed regulatory concepts and request for public comment; Two contract final reports complete (in-use emissions, activity, and repower/retrofit feasibility); Rulemaking surveys; Numerous individual meetings with stakeholders and site visits b) Maximizing reductions of PM, NOx, and GHG emissions, exact targets expected in late summer 2020. Diesel PM reductions are associated with decreased cancer risk adjacent to where CHC operate. c) Dock power and in-transit zero-emission operation requirements will likely require additional infrastructure to be installed at facilities for operation of equipment while docked, charging of on-board batteries, and fueling with alternative (i.e. zero-emission tailpipe) fuel | a) CARB’s current projection is Board Consideration by 2021 – a year after the original estimate of 2020. The delay is due to unpredicted complexity and new Board direction for other marine regulations (i.e. the At Berth Regulation), which required additional staff resources that could have been used to develop the new CHC regulation. b) November 2021 for Board consideration. c) The requirements of the amended CHC regulation will take effect in 2023, and have not been delayed by later Board consideration.
Heavy-Duty Vehicle Inspection and Maintenance | 128 | When emissions control systems are not operating correctly, in-use emissions can increase. CARB’s current inspection programs include the roadside Heavy-Duty Vehicle Inspection Program and the fleet Periodic Smoke Inspection Program. These regulations require heavy-duty vehicles operating in California be inspected for excessive smoke and tampering. In July 2018, CARB approved amendments to the Heavy-Duty Vehicle Inspection Program and the Periodic Smoke Inspection Program to reduce the smoke opacity limits to levels more appropriate for today’s modern engine technology. CARB is now exploring the development of a more comprehensive heavy-duty inspection and maintenance program that would help ensure all vehicle emissions control systems are maintained adequately throughout the vehicles’ operating lives. | Heavy-Duty Inspection & Maintenance | 13 | 2456 | Sacramento, Teleconference, Webcast, Webinar | 1 | 1. Draft Proposed HD I/M Regulatory Text Document | 2021-03-01 |  | 13 |  | 2021-12-09 |  |  |  | Staff is currently revising the Draft Proposed HD I/M Regulatory Text Document and expects to release it in the July timeframe. Discussions will continue with stakeholders to incorporate additional feedback necessary to finalize the proposed regulation before its official release in October 2021 for public comment. | This strategy requires CARB action during at least one board hearing. | a) CARB staff has conducted public workshops in 2019, 2020, and 2021, and plans at least one additional workshop or workgroup meeting for later this summer (2021) as program development continues. Staff has also conducted 9 focused HD I/M workgroup meetings to date with industry experts, environmental organizations, trucking associations, fleet representatives, and other governmental agencies. Staff will continue to engage with all interested stakeholders to develop and finalize the proposed regulation. b) HD I/M is a key measure in California's State Implementation Plan statewide strategy and one of the largest proposed near-term NOx reduction measures to meet the South Coast’s 2023 ozone attainment deadline and San Joaquin Valley's 2024 PM 2.5 attainment deadline. Staff is currently performing analyses to update emissions reduction estimates and health exposure reduction benefits. c) Coordinating with Caltrans on permitting for placement of RSDs, ALPRs, and potential OBD-data collection kiosks when sited on public roadways (RSDs, ALPRs) or at rest-stops or other Caltrans-owned land (for kiosks). There are no major land use or permitting issues for HD I/M and no expected CEQA impacts. | a) When included as a critical measure in the 2016 Mobile Source Plan and the 2016 Statewide SIP Strategy, staff anticipated that a comprehensive HD I/M program could be proposed to the Board in 2020. Recognizing that such a program would provide significant emission reductions and health benefits, the Legislature proposed and ultimately adopted critical legislation in 2019 (SB 210; Leyva) to provide CARB authority to develop/implement a robust HD I/M program unlike any other in the nation. The timing of the legislative process necessitated moving the Board date to the 2021 timeframe. b) CARB staff is scheduled to present a regulatory HD I/M program to the Board for its consideration at the December 9-10, 2021, Board meeting. c) With HD IM program implementation expected to be phased-in starting in 2023, the HD I/M program is expected to be on track to achieve near-term reductions in 2023/2024 at the community level. | 156.5228 |  |  | 0.86914 |  |  |  |  | 0.38407 | 60.7502 |  |  | 0.36555 |  |  |  |  | 0.42057
Cargo Handling Equipment Regulation Amendments | 129 | CARB staff is currently assessing the availability and performance of zero-emission technology to further reduce emissions. | Cargo Handling Equipment Regulation Amendments | 0 |  |  | 1 | 1. Cargo Handling Equipment Regulation to Transition to Zero-Emissions |  | 1. 3/14/2018 | 0 | [6 empty] | This strategy requires CARB action during at least one board hearing. | a) Tracking existing demonstration and pilot projects, meeting with some terminal operators to better understand operations and perspectives on zero-emission operation, participating in port air quality plan workgroups, task force meetings, and other updates. b) Targeting transition to zero-emission tailpipe technologies where possible. Exact targets expected in 2022. c) Zero-emission equipment will likely require additional infrastructure to be installed at facilities for operation of equipment, charging of on-board batteries, and fueling with alternative (i.e. zero-emission tailpipe) fuel. Substantial terminal reconfiguration and/or construction may be required.
Advanced Clean Fleet Rules | 129 | CARB is developing a medium and heavy-duty zeroemission fleet regulation with the goal of achieving a zero-emission truck and bus California fleet by 2045 everywhere feasible and significantly earlier for certain market segments such as last mile delivery and drayage applications. | Advanced Clean Fleet | 6 | 2499 | Diamond Bar, Webcast, GoToWebinar | 2 | 1. Preliminary Inventory Analysis 2. Cost Data & Methodology Draft | 1. 2/3/2020 2. 12/4/2020 |  | 6 | [6 empty] | This strategy requires CARB action during at least one board hearing. | a) Staff have been developing the regulation since 2019, have held a public workshop to kick off the effort, and have begun having individual meetings with stakeholders. b) TBD c) TBD |  | 153.674 |  |  | 2.7598 |  |  |  |  | 0.0044662 | 0.67429 |  |  | 0.012095 |  |  |  |  | 0.0049895
Transport Refrigeration Unit Regulations | 129 | Transport refrigeration units congregate at distribution centers, railyards, and other facilities, resulting in the potential for health risks to those that live and work nearby. CARB is working through a public process to consider new requirements to transition the transport refrigeration units fleet to zero emission operations by requiring both zero emission technology and supporting infrastructure. | Transport Refrigeration Unit Regulation | 9 | 864 | Fresno, Fontana, Riverside, Sacramento, Teleconference, Webinar | 2 | 1. Informational Document on Changes to TRU Rulemaking 2. Transport Refrigeration Unit Regulation Draft Regulatory Language for Stakeholder Review |  | 1. 1/22/21 2. 3/12/20 | 9 | [7 empty] | a) CARB has been developing the TRU Regulation since 2016, expects adoption of the Part 1 rulemaking in 2022, and will begin implementation in 2022. b) The TRU regulation will provide health, air quality, and climate benefits by reducing NOx, PM2.5, and GHG emissions. c) Installation of electric or fueling infrastructure at approximately 1,000 truck TRU home base facilities statewide. | a) CARB staff are now developing two rulemakings to transition diesel powered TRUs to zero emission technology. The decision to bifurcate the TRU rulemaking was made in response to Executive Order (EO) N 79-20. The previous draft TRU concept included requirements for zero emission truck TRUs; zero emission operation while stationary for trailer TRUs, domestic shipping container TRUs, and TRU generator sets; as well as zero emission infrastructure at applicable facilities. Staff determined that the zero-emission operation while stationary requirement did not meet the objective of the EO. b) Staff anticipate bringing the Part 1 rulemaking to the Board in 2021 and 2022 (two hearings); and the Part 2 rulemaking to the Board in 2024 (first hearing). c) Development of the Part 1 and Part 2 rulemakings to transition diesel-powered TRUs to zero emission will achieve additional emissions and health risk reductions. Implementation of the Part 1 rulemaking that focuses on transitioning truck TRUs to zero-emission will begin in 2022. | 19.3091 | 0.057179 |  | 0.21047 |  |  |  |  | 0.055154 | 0.42772 | 0.022151 |  | 0.052451 |  |  |  |  | 0.2492
Small Off-Road Engines | 129 | In 2020, CARB will consider new standards for small offroad engines (SORE), which are spark-ignition engines rated at or below 19 kilowatts and used primarily for lawn, garden, and other outdoor power equipment. | Small Off-Road Engine Amendment | 6 | 726 | Sacramento, Webinar | 13 | 1. Potential Amendments to Evaporative Emission Regulations 2. Potential Amendments to Exhaust Emission Regulations 3. Potential Amendments to TP-901 4. Potential Amendments to TP-902 5. Potential Amendments to CP-902 6. Potential Amendments to Part 1054 7. Potential Amendments to Part 1065 8. Potential Evaporative Emission Regulation Amendments 9. Potential Exhaust Emission Regulation Amendments 10. Potential Amendments to TP-901 11. Potential Amendments to TP-902 12. Potential Amendments to CP-902 13. Small Off-Road Engines Fact Sheet |  | 1. 3/24/21 2. 3/24/21 3. 3/24/21 4. 3/24/21 5. 3/24/21 6. 3/24/21 7. 3/24/21 8. 6/9/20 9. 6/9/20 10. 6/9/20 11. 6/9/20 12. 6/9/20 13. 2/4/19 | 6 | [7 empty] | a) CARB has conducted three public workshops on the potential amendments in September 2019, June 2020, and March 2021, and expects to take the rulemaking package to the Board in 2021 or 2022. If the Board adopts the proposed regulation and OAL approves it, CARB anticipates it will begin implementation of the regulation in 2024 or 2025. b) Premature cardiopulmonary mortality cases avoided: 892 Hospitalizations for cardiovascular illness avoided: 142 Hospitalizations for acute respiratory illness avoided: 169 Emergency room visits avoided: 439 (These are based on regulatory scenario presented in the March 2021 workshop. Changes may be made before ISOR is published.) c) None |  | 89.8852 | 7.373 |  | 4.5189 |  |  |  |  | 0.19601 | 18.2 | 0.13836 |  | 0.31939 |  |  |  |  | 0.073865
Advanced Clean Cars II | 130 | CARB staff is developing the Advanced Clean Cars II regulations, which will seek to reduce criteria and greenhouse gas emissions from new light- and medium-duty vehicles beyond the 2025 model year, and increase the number of zero emission vehicles for sale | Advanced Clean Cars 2 | 3 | 1017 | Virtual | 5 | 1. Workshop Presentation 2. Workshop Presentation 3. Proposed Puff Equation: Evaporative Emissions 4. Proposed 3 Bin Moving Average Window Method for Chassis Certified Medium Duty Vehicles 5. Draft ZEV Data Parameters |  | 1. 9/24/20 2. 5/19/21 3. 5/19/21 4. 5/19/21 5. 5/26/21 | 2 | [5 empty] | CARB staff will host at least two additional workshops in 2021 (in the summer and fall) on the Advanced Clean Cars II rulemaking before the targeted June 2022 board hearing. | The Advanced Clean Cars 2 Regulation is tentatively scheduled for June 2022. | a) CARB has been developing Advanced Clean Cars II since 2017 and expects board adoption in 2022, with most provisions taking effect as soon as model year 2026. b) Light duty vehicles continue to be a significant contributor of greenhouse gases to the California inventory. The proposed regulation will result in significant decreases in greenhouse gas emissions. Additionally, increased ZEVs and further emission controls for combustion vehicles will contribute to long term criteria pollutant reductions. c) An indirect impact of a larger market share of ZEVs resulting from these regulations will be the associated development of charging and hydrogen infrastructure to fuel these vehicles. Constructing this infrastructure requires permits and may increase development outside of existing paved areas, for instance separate from current gasoline fueling stations.
Commercial Cooking Suggested Control Measure | 130 | This strategy consists of a twophase process to evaluate California’s current emission reduction requirements for commercial cooking operations that prepare food for human consumption, and if necessary, make improvements to achieve additional reductions in particulate matter 10 microns or less in diameter (PM10), particulate matter 2.5 microns or less in diameter (PM2.5) and volatile organic compound emissions that contribute to ozone formation. | Commercial Cooking Suggested Control Measure | 0 |  |  | 0 | [11 empty] | a) Considering the process and resources needed to develop a technical assessment for commercial cooking b) TBD c) TBD
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 2.CARB Enforcement
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
San Joaquin Valley APCD: Stockton
|  |  |  | Outreach |  |  | Inspections |  |  |  | Coordination |  |  |  |  | SB 1 Implementation |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Strategy Description in CERP | Agency | Events within Community (Qty) | Attendees (Qty) | Locations of Events (Text) | Complaint Inspections (Qty) | CERP Inspections (Qty) | NOVs (Qty) | Compliance Rate (%) | Agencies Engaged (Qty) | Names of Agencies Engaged (Text) | Meetings (Qty) | Resulting Actions (Qty) | Description of Resulting Actions (Text) | Statewide Vehicle Turnover (Qty) | Community Registration Holds (Qty) | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
1 | 136 | Coordinate and conduct inspections of stationary sources with Air District staff | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X |  |  |  |  | Public comments on the CERP Draft for Port Side Community were received in May 2021. The final version of the CERP is pending approval from CSC (planned for June 2021), the San Diego County Air Pollution Control District Board (planned for July 2021) and CARB (planned for September 2021)
2 | 136 | Achieve compliance with the Truck and Bus Regulation via Senate Bill 1 | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
3 | 136 | Provide Annual Report of Enforcement Activities | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
4 | 136 | CARB will seek opportunities to coordinate with other agencies with enforcement authority in Portside Environmental Justice Neighborhoods, including but not limited to the City and San Diego and Port of San Diego. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
5 | 136 | CARB is committed to enhancing the quality of enforcement data for the Portside Environmental Justice Neighborhoods community. Moving forward, CARB will maintain the location of enforcement activity and received complaints to provide the community steering committee with the most accurate data available. CARB has recently launched a visualization tool that makes CARB enforcement data more transparent and available. CARB’s visualization tool provides access to community specific enforcement data and is publicly available online by visiting https://webmaps.arb.ca.gov/edvs/. | CARB | N/A | N/A | N/A | 2 HDDV inspections: 1 enforcement action taken, 1 under investigation | 293 HDDV inspections (does not include idling) within community boundaries; 134 inspections within 0.5-mile buffer outside of boundaries | 69 violations within boundaries; 20 inspections within 0.5-mile buffer | 79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
6 | 136 | CARB will develop and offer training opportunities to the Portside Environmental Justice Neighborhoods community. Information will cover topics like the fundamentals of enforcement, how the enforcement process works, instructions on filing a thorough complaint, and what to expect from the enforcement process after filing a complaint. Through this program, community members will be able to better support CARB or air district enforcement processes. CARB will also develop online trainings in the future. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
7 | 136 | CARB staff are committed to updating enforcement strategies as requested by the community steering committee, if those strategies are enforceable by CARB staff or if CARB can reasonably accommodate the request. | CARB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action A3: Develop Plan to Quantify and Prioritize the Community Health Risks from Air Pollutants | 144 | Determine, in consultation with the Community Steering Committee and CARB, the goals and objectives of the health risk analysis; Based on the goals and objectives develop a work plan that articulates and evaluates the inputs, processes, deliverables, and timelines needed in quantifying and prioritizing the health risks and establish options considering various timeframes and resources needed, including the need and scope of any subsequent updates; Determine how the planning emission inventories developed for this Community Emissions Reduction Program (in Chapter 3) can be utilized to quantify the health risks. | CARB, SDAPCD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action B1: Create Additional Flexibility for Mobile Source Incentives | 147 | Work with the CSC and the public to identify and prioritize opportunities that could benefit from incentive funding. Work with CARB to increase flexibility to provide funding for other projects in the Portside community through the Community Air Protection Incentives Guideline process. Potential flexibilities include: Modified cost-effectiveness limits for zero-emission Moyer-type projects; Eligibility for new purchase without scrappage requirements; Eligibility for supporting infrastructure; Provide mechanism for funding pilot projects to demonstrate new technologies; Eligibility for projects to reduce exposure including indoor air filtration, tree and vegetation plantings; Eligibility for projects that reduce emission from passenger car use, including incentives for zero and near-zero emission vehicles, transit passes, bicycle, and pedestrian projects, and others; Consideration of proximity of emissions to sensitive receptors, such as schools. | CARB, SDAPCD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action B2: Reduce Emissions from Passenger Vehicles | 148 | Implement incentive program for zero and near-zero vehicles for low income residents in disadvantaged communities (Clean Cars 4 All or similar); Implement EV charging infrastructure incentive program (CALeVIP); Coordinate with other jurisdictions and agencies to support improvements to pedestrian, bicycle, shared mobility services, and transit infrastructure | CARB, SDAPCD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action D2: Evaluate the Feasibility of Expanding Mobile Source Enforcement Program | 162 | Work with the California Air Resources Board (CARB) to evaluate the feasibility of obtaining authority to enforce additional mobile source regulations including; Marine - Commercial Harbor Craft Regulation; On-Road and Cargo Handling - Mobile Cargo Handling Equipment Regulation, Solid Waste Collection Vehicle Regulation, Tractor-Trailer Greenhouse Gas (TTGHG) Regulation; Conduct a cost analysis to evaluate the feasibility of expanding the mobile source program by increasing the number of staff members to conduct additional inspections under the existing MOU. | CARB, SDAPCD | N/A | N/A | N/A | N/A | 240 Railroad and Marine (RRM) program inspections within boundaries; 28 RRM inspections within 0.5-mile buffer outside of boundaries | 2 violations, 2 pending within boundaries | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action D6: Promote enforcement of existing air quality rules and regulations pertaining to mobile sources. | 167 | Evaluating the feasibility of expanding enforcement of truck idling regulations within the Portside Community. | CARB, SDAPCD | N/A | N/A | N/A | N/A | 68 idling inspections within boundaries; 70 idling inspections within 0.5-mile buffer outside of boundaries | 0 violations | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
Action G2: Reduce Emissions from Ships at Berth | 191 | Grant funding support for shore power or equivalent reductions in ship hoteling emissions; Emission reductions from ship hoteling or innovative concepts, starting with pilot testing in 2024; Utilize existing ship-to-shore power infrastructure to shut down main and auxiliary engines | CARB, SDGE, PSD, NBSD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | X
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 3.CARB Guidance
Annual Progress Reports for AB 617 Community Emissions Reduction Programs | [5 empty] | DUE OCTOBER 1
DRAFT Data Collection Template
CARB staff are providing the following information for all CARB strategies included in the community emissions reduction program
San Joaquin Valley APCD: Stockton
[6 empty] | Outreach |  |  | Pre-Guidance Documents |  |  |  | Guidance Development Dates |  |  | Estimated % Complete or Strategy Implementation (place "X" in appropriate column) |  |  |  | QUALITATIVE STATUS UPDATE | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID in CERP | Page # in CERP | Page # in Blueprint | Strategy Description in CERP | Agency | CARB Guidance Title | Events Statewide (Qty) | Attendees (Qty) | Locations of Events (Text) | Public Documents Released (Qty) | Title of Document (Text) | Draft Document Released (Date) | Final Document Released (Date) | Draft Guidance Released | Final Guidance Released | Board Hearings | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
- This metric will not be tracked by CARB.
* | - As of the publish date of this documents, this metric either hasn't been collected, or the program hasn't been developed to a point to be able to quantify this metric.

## 4.CARB Incentive
Annual Progress Reports for AB 617 Community Emissions Reduction Programs |  |  |  | DUE OCTOBER 1
DRAFT Data Collection Template
CARB is providing the following information on incentive programs benefiting East Los Angeles
San Joaquin Valley APCD: Stockton
|  | Incentive Project Funds |  |  |  |  | Estimated Project Emissions Reductions |  |  | Outreach
|  | 2017 | 2018 | 2019 | 2020 | Cumulative Total | Oxides of Nitrogen (Tons) | Reactive Organic Gasses (tons) | PM 2.5 (tons) | Events | Attendees
Air Resources Board Programs | Carl Moyer Memorial Air Quality Standards Attainment Program | 3750000 |  |  |  | 3750000 | 161.6 | 11.1 | 4.8
| Clean Cars For All |  | 115368 | 378636 | 524000 | 1018004 | 1.3 | 0.2 | 0
| Clean Off Road Equipment Voucher Incentive Project |  |  |  | 1290000 | 1290000 | 0.7 | 0 | 0
| Clean Vehicle Rebate Project | 64750 | 119000 | 208500 | 53500 | 445750 | 0.1 | 0 | 0.1
| Community Air Grants |  |  |  | 100000 | 100000 | - | - | -
| Enhanced Fleet Modernization Program Plus-Up | 332701 |  |  |  | 332701 | 0.4 | 0 | 0
| Funding Agricultural Replacement Measures for Emission Reductions |  |  | 13722 |  | 13722 | 0.3 | 0 | 0
| Hybrid and Zero-Emission Truck and Bus Voucher Incentive Project | 2965000 | 825000 |  | 900000 | 4690000 | 34.7 | 0.3 | 2.4
| Off-Road Advanced Technology Demonstration Project |  | 722555 |  |  | 722555 | 0 | 0 | 0
| Supplemental Environmental Projects |  |  |  | 95896 | 95896
| Truck Loan Assistance Program | 2585960.88 |  | 1415251.7 | 94800 | 4096012.58
Total By State Agency | Air Resources Board | 9698411.88 | 1781923 | 2016109.7 | 3058196 | 16554640.58 | 199.2 | 11.7 | 7.3 | 9 | 302
| Department of Community Services and Development | 766858 | 176953 |  |  | 943811 | 0.8 | 0.1 | 0.1
| Department of Forestry and Fire Protection | 655267 |  | 0 | 0 | 655267 | - | - | - | 4 | 71
| Department of Transportation | 397733 | 566109 | 1055071 | 1707937 | 3726850 | 0.7 | 0.1 | 0 | 1 | 53
| Strategic Growth Council | 5857096 | 9141370 |  |  | 14998466 | - | - | - | 3 | 68
| Grand Total | 17375365.88 | 11666355 | 3071180.7 | 4766133 | 36879034.58 | 200.6 | 11.9 | 7.4 | 17 | 494

## CARB Metrics Glossary
Glossary of CARB Metrics
Description of metrics that CARB will track and provide to the District, as shown on the tabs in this spreadsheet.
METRICS | DESCRIPTIONS
Outreach
Events statewide (Qty) | Number of CARB outreach/training events.
Attendees (Qty) | Number of attendees at CARB outreach/training events.
Locations of Events (Text) | List locations where outreach events are held (e.g., city names)
Enforcement and Inspections
Complaint Inspections (Qty) | Number of complaint inspections conducted by CARB.
CERP Inspections (Qty) | Number of inspections based on CERP strategies and conducted by CARB.
NOVs (Qty) | Number of notices of violation (NOVs) issued in the community by CARB.
Compliance Rate (%) | Percentage of CARB inspections that were found to be in compliance with CARB regulations.
Statewide vehicle turnover | Number of heavy duty vehicles that have permanently stopped operating in California, as a result of SB 1 implementation.
Community registration holds | Number of heavy duty vehicle registrations in the community that have been denied due to non-compliance with SB 1 provisions.
Coordination
Agencies Engaged (Qty) | Number of agencies engaged by CARB.
Names of Agencies Engaged (Text) | List names of agencies engaged by CARB.
Meetings (Qty) | Number of CARB meetings with other agencies
Resulting Actions (Qty) | Number of actions resulting from coordination with other agencies.
Description of Resulting Actions (Text) | Provide a brief description of actions resulting from coordination with other agencies.
Non-Regulatory Documents (concept papers, white-papers, etc.)
Public Documents Released (Qty) | Number of public document(s) released
Title of Non-Regulatory Document(s) (Text) | Title of non-regulatory document(s) associated with the development of statewide measures
Draft document released (Date) | Date when CARB released the draft non-regulatory document(s)
Final document released (Date) | Date when CARB released the final non-regulatory document(s)
Regulatory Process Milestones
Workshops/Webinars | Number of public workshop(s) or webinar(s) conducted providing the opportunity for stakeholders, including community members, to influence staff work prior to going to Board.
Release of 45 day or 60 day package | Start of Office of Administrative Law clock, providing the opportunity for stakeholders, including community members, to begin influencing Board member perspectives/decisions.
First Board hearing | Date when CARB's Governing Board holds initial public hearings (may be more than 1)
Potential 15 day changes | Date when CARB released "15-day changes" with revisions to draft regulatory language for public comment
Final Board hearing | Date when CARB's Governing Board approves the adoption of the regulation
OAL approval | Date when the California Office of Administrative Law approves the regulation
Community Criteria and Toxics Emissions Reductions Based on CARB’s Community-Scale Inventory
Forecasted baseline emissions (tpy) (2024) for all pollutants in planning inventory | Forecasted baseline emissions without the CARB measure
Draft emissions reductions, as available (tpy) (2024) for all regulatory pollutants in the planning inventory | Draft forecasted emissions reductions in 2024 with implementation of CARB measure, released during the regulatory development process
Final emissions reductions (tpy) (2024) for all regulatory pollutants in the planning inventory | Final forecasted emissions reductions in 2024 with implementation of CARB measure, after the regulation is adopted by CARB's Board

## DISTRICT Vegetative Barriers
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Vegetative Barriers Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Vegetative Barriers Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
VB.1 | 65 | Incentive program for the installation of vegetative barriers around/near sources of concern |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented. 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. 5. Number of facilities that have installed vegetative barriers as a result of District outreach and partnership programs. 6. Footage of vegetative barrier installed along roads or train routes as a result of District outreach and partnership programs. 7. Number of community steering committee meetings with City/County/Caltrans that include agenda items to discuss vegetative barrier installations in the community. | Incentives, Collaboration |  |  | X | [16 empty] | TCC/Little Manila/Port of Stockton |  | a) Subcommittee formed, District gathering information from TCC/Little Manila/Port of Stockton about current greening efforts. District to develop and send draft of project plan to subcommittee

## DISTRICT Urban Greening
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Urban Greening Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Urban Greening Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
UG.1 | 68 | The purpose of this strategy is to identify and support efforts toincrease urban greening/forestry to improve air quality for residents in the Stockton community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented. 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. 5. Number of district meetings with City and County to discuss opportunities for increased urban greening and forestry in the community. | Incentives, Collaboration |  |  | X | [18 empty] | a) Subcommittee formed, District gathering information from TCC/Little Manila/Port of Stockton about current greening efforts. District to develop and send draft of project plan to subcommittee

## DISTRICT Exposure Red Schools
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Incentives Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Incentives Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
SC.1 | 71 | This strategy would provide up to $2,640,000 in incentive funding for schools within the Stockton boundary to install advanced air filtration systems, utilizing existing Community Air Protection Program guidelines. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (filtration systems). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  |  | X | [18 empty] | Subcommittee interest to be gathered at December 1, 2021 CSC meeting
SC.2 | 71 | The goal of this strategy is to reduce children’s exposure to unhealthy air by increasingthe enrollment of schools in the Healthy Air Living (HAL) Schools program to decrease vehicle idling, limit children’s outdoor activity during episodes of poor air quality, and educate student about protecting our air. |  | 1. Number of school districts and schools registered for the District’s HAL Schools Program. 2. Number of schools with advanced filtration systems installed, and number of classrooms with room filtration units installed at each school. 3. Number of educational events held related to health-protective measures for the public. | Public Information And Outreach |  |  | X | [18 empty] | Subcommittee interest to be gathered at December 1, 2021 CSC meeting

## DISTRICT Indoor Air Quality
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Exposure Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Indoor Air Quality Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Indoor Air Quality Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
IAQ.1 | 73 | This strategy would establish an incentive program for residential air filtration for community residents near sources of air pollution, and increase outreach and access to programs available for low-income residents in Stockton to receive weatherization services. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented. 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentive |  |  | X | [18 empty] | Subcommittee interest to be gathered at December 1, 2021 CSC meeting

## DISTRICT Community Outreach
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Community Outreach Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Community Outreach Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
O.1 | 74 | This strategy would aim to increase myRAAN website registrations, Valley Air App downloads, and social media followers among members of the community. In addition, this strategy would increase awareness of air quality issues with workshops hosted in locations commonly available to the public such as libraries, schools, and community, health, or recreation centers and on Zoom or other online platforms. |  | 1. Number of outreach events/activities to increase community awareness of air quality. | Outreach |  |  | X | [18 empty] | Subcommittee interest to be gathered at December 1, 2021 CSC meeting

## DISTRICT Lawn and Garden
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Lawn and Garden Equipment Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Lawn and Garden Equipment Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
LG.1 | 77 | Using existing District Board-approved criteria, this strategy will provide enhanced outreach and education as well as higher incentive funds to local Stockton residents to encourage participation and maximize local emission reductions within the community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (lawn and garden units). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives, Outreach |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
LG.2 | 78 | This strategy will provide enhanced outreach and access to available incentive funds offered by the District, utilizing Board-approved criteria. The goal of this measure is to replace 5 pieces of commercial grade gas powered lawn and garden equipment at an expected cost of up to $20,000 per unit. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (lawn and garden units). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives, Outreach |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting

## DISTRICT Land Use
Annual Progress Report for AB 617 Community Emissions Reduction Programs
DRAFT Data Collection Template
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Emissions Exposure and Land Use Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Emissions Exposure and Land Use Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
LU.1 | 80 | Reducing emissions from motor vehicles through the implementation of alternate modes of transportation directly contributes to decreasing public exposure to vehicle emissions, such as diesel particulate matter which adversely impacts human health. Land use decisions are critical in contributing to the improvement in air quality within a community and should be geared towards promoting strategies aimed at reducing vehicle miles traveled by increasing community walkability. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented. 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program and projects that reduce VMT. 5. Number of meetings with City of Shafter to discuss district support of projects that reduce VMT, plus ongoing support as needed. | Collaboration |  | X
LU.2 | 81 | The purpose of this measure is to assess current bike path infrastructure and seek out additional funding opportunities to make the community more bike and walk friendly. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (bike paths). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X
LU.3 | 81 | The goal of this strategy is to enhance inter-agency and community collaboration to reduce the impact of pollution from motor vehicles by prioritizing pedestrian-friendly land-use design elements around downtown Stockton. |  |  | Land Use |  | X
LU.4 | 82 | The goal of this strategy is to better understand, and where feasible, mitigate the impact of algae blooms on air quality. While the District, the City of Stockton and the Central Valley Regional Water Quality Control Board (CVWB) have committed to extensive interagency cooperation and action in this Stockton Community EmissionsReduction Program (CERP), additional opportunities may present themselves in future discussions involving the CSC, the public, the City, and the District, especially as implementation of the CERP progresses. |  | Subcommittee interest to be gathered at December 1, 2021 CSC meeting | Collaboration |  | X | [19 empty] | Subcommittee interest to be gathered at December 1, 2021 CSC meeting

## DISTRICT Heavy Duty Mobile
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Heavy Duty Mobile Sources Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Heavy Duty Mobile Sources Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
HD.1 | 86 | Community Steering Committee members have suggested that a study should be performed to assess the existing heavy-duty diesel truck routes in and around the Port of Stockton and the nearby neighborhoods, including the Boggs Tract neighborhood. The study will focus on whether there are other routes which will result in reduced exposure to toxic air contaminants by residents in the nearby neighborhoods. |  | 1. Number of interactions with other agencies (e.g, city, county, State) to address truck rerouting. 2. Date when a traffic study is released. 2. Number of outreach events/activities related to truck rerouting. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
HD.2 | 87 | This strategy would provide enhanced outreach and access to incentive funding for zero and near-zero emissions, clean truck technologies that are domiciled and operating within the community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (trucks). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
HD.3 | 87 | Utilizing Board-approved methodology and funding levels the District will work closely with businesses, public agencies, and fueling providers to support and incentivize the development of clean-vehicle fueling infrastructure in the area of the community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (charging plugs). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives, Public Information And Outreach |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
HD.4 | 88 | This strategy would provide funding to launch a program in the Stockton community. The District would leverage experience from the Proposition 1B Goods Movement Emission Reduction Program in order to design a program that would fund the purchase and installation of electrical infrastructure and/or equipment to enable heating, cooling, and other use of cab power for parked trucks at truck stops in the Stockton area. |  |  | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
HD.5 | 89 | The District will partner with CARB to conduct additional targeted anti-idling enforcement efforts in the Stockton community with established benchmarks. These benchmarks include anti-idling surveillance to occur at least once per quarter for the next 5 years. |  | For enhanced enforcement efforts in the community, track the following: 1. Inspections conducted including type, date, and location. 2. Notices of violations issued including date, recipient, and regulation cited. 3. Number of complaints received by type and their resolution. 4. Percentage of notices of violations/notices to comply that have been resolved. | Enforcement |  |  | X | [18 empty] | Subcommittee interest for enforcement measures to be gathered at December 1, 2021 CSC meeting
HD.6 | 89 | To provide increased outreach and access to incentive funding for the replacement of older, high polluting school buses with new zero-emission school buses operating within the Stockton Unified School District. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (school buses). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
HD.7 | 90 | To provide incentive funding for the replacement of older, highpolluting switcher locomotives with new clean-technology switcher locomotives operating within and surrounding the Stockton community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (switcher locomotives). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting

## DISTRICT Passenger Cars
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Older/High Polluting Passenger Car Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Older/High Polluting Passenger Car Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
TP.1 | 94 | The goal of this strategy is to reduce emissions associated with passenger vehicles by replacing 100 vehicles with newer,more fuel efficient models, and providing additional incentives for Level 2 residential chargers in the Stockton community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (vehicle repairs). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives, Outreach |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
TP.2 | 94 | Incentive program for the replacement of passenger vehicles with battery electric or plug in hybrid vehicles |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (clean air vehicles). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives, Public Information And Outreach |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
TP.3 | 95 | This strategy would provide incentive funding for publically accessible charging infrastructure to private and public entities in the Stockton community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (electric chargers). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
TP.4 | 96 | This strategy will provide up to $15,000 per training coursefor at least 10 alternative fuel mechanic training courses provided by an appropriate entity. While there are no direct emission reductions associated with this measure, this measure supports the emission reductions associated with additional electric vehicle deployment. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (training events). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  |  | X | [18 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
TP.5 | 97 | This strategy provides funding for a partnering car share provider to launch a program in the Stockton community. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (cars available in car sharing program). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  |  | X | [18 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting

## DISTRICT Residential Burning
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Residential Burning Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Residential Burning Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
RB.1 | 99 | The proposed program under this strategy would offer up to $3,000 to replace an existing wood burning device with a natural gas device and up to $4,000 for an eligible electric heating source, such as an electric heat pump. |  | For incentive projects in the community, track the following: 1. Dollar amounts invested. 2. Number of projects implemented (devices). 3. Emissions reductions. 4. Number of outreach events/activities to promote this incentive program. | Incentives |  | X | [19 empty] | Subcommittee interest for outreach for incentives measures to be gathered at December 1, 2021 CSC meeting
RB.2 | 100 | This strategy would create a series of four (4) public workshops to educate Stockton residents about wood burning topics and to address questions and concerns interactively and accessibly within a forum setting |  | 1. Number of outreach events/activities to increase community awareness of wood burning impacts. | Outreach |  | X | [19 empty] | Subcommittee interest for outreach measures to be gathered at December 1, 2021 CSC meeting
RB.3 | 100 | This strategy would include working with the City of Stockton and the fire agencies to better understand the illegal open burning issues within the AB 617 community, establish a series of public workshops to educate Stockton residents about illegal open burning, the health impacts of burning waste, and to address questions and concerns interactively and accessibly within a forum setting either in person or in an online platform such as Zoom. |  | 1. Number of outreach events/activities, to reduce illegal burning of residential waste. | Outreach |  | X | [19 empty] | Subcommittee interest for outreach measures to be gathered at December 1, 2021 CSC meeting

## DISTRICT Stationary Sources
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Stationary Sources Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Stationary Sources Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
SS.1 | 105 | The District will increase the frequency of inspection at each facility within the Stockton community that has had an emission-based violation over the past three (3) years. These facilities will be inspected at least twice per calendar year for the next five (5) years or until the facility has four (4) consecutive inspections without an emissions violation, whichever occurs first. |  | For enhanced enforcement of stationary sources in the community, track the following: 1. Inspections conducted including type, date, and location. 2. Notices of violations issued including date, recipient, and regulation cited. 3. Number of complaints received by type and their resolution. 4. Percentage of notices of violations/notices to comply that have been resolved. 5. Status update on completion of the Enforcement Plan (2 inspections per year for 5 years or until 4 consecutive inspections with no violation). | Enforcement |  |  | X | [18 empty] | Subcommittee interest for enforcement measures to be gathered at December 1, 2021 CSC meeting
SS.2 | 106 | In addition to the Best Available Retrofit Control Technology (BARCT) implementation schedule above, the District will be analyzing District Rule 4352 -Solid Fuel-Fired Boilers, Steam Generators and Process Heaterstopursue additional emission reduction opportunities beyond BARCT. |  | For the rules that the district has identified, track the following: 1. Number of rules that the district has evaluated, per the PM2.5 Plan schedule, for additional reductions beyond BARCT. 2. Number of outreach events/activities on the rule evaluations and amendments. 3. Number of draft rule amendments that the district has released. 4. Number of rules that the district has amended. | Regulatory |  |  | X | [18 empty] | Subcommittee interest for enforcement measures to be gathered at December 1, 2021 CSC meeting
SS.3 | 106 | This strategy will expedite the review of stationary sources of pollution in the community that are currently being reassessed under the Air Toxics "Hot Spots" Information and Assessment Act (AB 2588). |  | For the AB 2588 facilities that the district has identified, track the following: 1. Number of expedited facility risk assessments that the district has completed for community facilities. 2. Number of outreach events/activities on the facility reassessments. 3. Number of facilities that need to develop new/revised risk reduction plans after reassessment. 4. Number of facilities that have completed their new/revised risk reduction plans. | Regulatory |  |  |  | X

## DISTRICT Dust in the Community
Annual Progress Report for AB 617 Community Emissions Reduction Programs
Please provide the following information for EACH STRATEGY in your community emissions reduction program
San Joaquin Valley APCD: Stockton
[7 empty] | ESTIMATED % COMPLETE FOR STRATEGY IMPLEMENTATION (place "X" in appropriate column) |  |  |  | OUTREACH/TRAINING EVENTS METRICS |  |  | ENHANCED ENFORCEMENT METRICS |  |  |  |  | INCENTIVE PROJECTS METRICS |  |  | REGULATORY ACTIONS |  | COORDINATION |  | BOARD ACTIONS (if applicable) | ADDITIONAL INFORMATION FROM BLUEPRINT (if applicable)
Strategy Number/ ID | Page # in Plan | DISTRICT STRATEGIES Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Dust in the Community Strategies | DISTRICT GOALS Goals for Each Strategy in Chapter 4 Strategies to Reduce the Cumulative Exposure Burden in Stockton - Dust in the Community Strategies | DISTRICT METRICS Metrics to Track Progress, Based on District Goals | Category | Insert Qualitative Status Update or Additional Notes Here or Provide an Attachment | 0% (have not started implementing strategy) | 1-50% (have begun implementing strategy) | 51-99% (strategy is mostly implemented) | 100% (strategy is fully implemented) | Topic of Outreach/ Training Events (Text) | Number of Outreach Events (Qty) | Locations of Outreach Events (Text) | Number of Inspections Conducted (Qty) | Number of NOVs Issued (Qty) | Number of Complaints Received (Qty) | Number of NOVs That Have Been Resolved (Qty) | Non-Compliance Rate (%) | Dollar Amounts Invested ($) | Number of Projects Implemented (Qty and Type) | Emissions Reductions (Tons/Yr by Pollutant) | Release of Draft Regulatory Amendments (Qty, Dates) | Date when Regulatory Actions are Finalized (Date) | Number of Interactions with Other Agencies (Qty) | Names of Other Agencies (Text) | If the strategy requires action by the Air District Board or the CARB Governing Board, describe any Board meetings for this strategy. | If the strategy is already being implemented: (a) Describe the steps that have been taken to-date; (b) Characterize the health-related emissions and exposure reduction benefits of this strategy; (c) Characterize any relevant land use or permitting issues for this strategy. | If the strategy has not been implemented and is past its due date, provide a status update: (a) Explain why implementation is delayed; (b) Provide a proposed new timeframe or substitute strategy; (c) Discuss how the overall emissions reduction targets will still be achieved in within the five-year timeframe
FD.1 | 115 | The goal of this strategy is to limit the potential for localized air quality impacts associated with fugitive dust from construction/earthmoving activities and open areas subject to District Regulation VIII. |  | For enhanced enforcement of fugitive dust sources in the community, track the following: 1. Inspections/surveillance efforts conducted including type, date, and location. 2. Notices of violations issued including date, recipient, and regulation cited. 3. Number of complaints received by type and their resolution. 4. Percentage of notices of violations/notices to comply that have been resolved. 5. Status update on completion of targeted enforcement efforts (1 per quarter in 2 and 3 quarters for 5 years). | Enforcement |  |  | X | [18 empty] | Subcommittee interest for enforcement measures to be gathered at December 1, 2021 CSC meeting